## Matters
Closing Pipeline — Matters
One row per matter. Edited through the web app.
MatterID | MatterName | ClientNames | PropertyAddress | State | County | FileType | TransactionType | ContractDate | TargetClosingDate | PurchasePriceOrLoanAmt | OpposingCounsel | TitleCompany | Lender | Paralegal | LoanType | LoanEstimateDate | ChangedCircumstancesFlag | CurrentPhase | Status | DateCreated | DateUpdated
2026-001 | Smith Purch. — 4823 Ridgeway Ave | John & Jane Smith | 4823 Ridgeway Ave, Cincinnati OH 45209 | Ohio | Hamilton | ST | Residential Purchase | 2026-04-15 | 2026-05-28 | 425000 | Anderson & Webb LLP | Fidelity National Title | Fifth Third Bank | Missy | Conventional | 2026-04-20 | No |  | Active | 2026-04-15 | 2026-05-10
2026-002 | Patel Refi. — 1209 Oak St | Raj & Priya Patel | 1209 Oak Street, Lexington KY 40502 | Kentucky | Fayette | RK | Residential Refi | 2026-05-01 | 2026-05-25 | 312000 |  | Stewart Title | Sharefax | Missy | Conventional | 2026-05-03 | No |  | Active | 2026-05-01 | 2026-05-15
2026-003 | Riverdale Comm. Purch. | Riverdale Holdings LLC | 850 Industrial Pkwy, Indianapolis IN 46225 | Indiana | Marion | ST | Commercial Purchase | 2026-03-28 | 2026-06-15 | 2850000 | Frost Brown Todd LLC | Old Republic Title | PNC Bank | Missy |  |  |  |  | Active | 2026-03-28 | 2026-05-18
2026-004 | Hernandez Cash — 217 Maple Dr | Maria Hernandez | 217 Maple Dr, Florence KY 41042 | Kentucky | Boone | ST | Residential Cash Sale | 2026-05-08 | 2026-05-26 | 198500 |  | Chicago Title |  | Missy |  |  |  |  | Active | 2026-05-08 | 2026-05-08
2026-005 | Chen Purch. — 6740 Beechmont | David & Linda Chen | 6740 Beechmont Ave, Cincinnati OH 45230 | Ohio | Hamilton | RK | Residential Purchase | 2026-05-12 | 2026-06-22 | 565000 | Graydon Head | Fidelity National Title | Huntington Bank | Missy | FHA | 2026-05-14 | No |  | Active | 2026-05-12 | 2026-05-20
2026-006 | Jackson — Closed | Terrence Jackson | 88 Mill Rd, Cincinnati OH 45239 | Ohio | Hamilton | ST | Residential Purchase | 2026-02-10 | 2026-04-30 | 285000 | Keating Muething | Stewart Title | US Bank | Missy | Conventional | 2026-02-15 | No |  | Closed | 2026-02-10 | 2026-04-30

## Notes
Notes Log
Append-only. One row per note. Linked to a matter via MatterID.
NoteID | MatterID | Timestamp | Author | NoteText
N1715000001 | 2026-001 | 2026-05-18 14:32 | Missy | Title commitment received from Fidelity. Reviewed exceptions, none unusual.
N1715000002 | 2026-001 | 2026-05-20 09:15 | Lillian Vrolijk | Spoke with lender — clear to close pending appraisal. CD expected by 5/24.
N1715000003 | 2026-002 | 2026-05-16 11:00 | Missy | Sharefax-specific tax info sheet drafted.
N1715000004 | 2026-003 | 2026-05-12 16:45 | Lillian Vrolijk | Environmental Phase I came back clean. Tenant estoppels in progress.

## ChecklistStatus
Document Checklist — Status per matter
Prepared = document is drafted; Approved = revisions complete, ready for print/signature; NA = item does not apply to this matter.
MatterID | ItemKey | ChecklistItem | Prepared | PreparedInitials | PreparedDate | Approved | ApprovedInitials | ApprovedDate | NA | Notes
2026-001 | GEN001 | Title Commitment / Opinion Letter | N |  |  | N |  |  | N
2026-001 | GEN002 | Title Update Needed/Requested | Y | MM | 2026-04-27 | Y | LV | 2026-04-24 | N
2026-001 | GEN003 | Title Update Received | N |  |  | N |  |  | N
2026-001 | GEN004 | Proof of insurance | N |  |  | N |  |  | N
2026-001 | GEN005 | Survey | N |  |  | N |  |  | N
2026-001 | GEN006 | Deed | Y | MM | 2026-04-20 | Y | LV | 2026-04-22 | N
2026-001 | GEN007 | Ohio - Conveyance Statement | Y | MM | 2026-04-20 | Y | LV | 2026-05-07 | N
2026-001 | GEN008 | CPC Letter | Y | MM | 2026-05-07 | Y | LV | 2026-05-03 | N
2026-001 | GEN009 | Indiana Sales Disclosure Form | Y | MM | 2026-05-15 | Y | LV | 2026-05-17 | N
2026-001 | GEN010 | Indiana State Form 51781 (Yellow) | Y | MM | 2026-05-12 | N |  |  | N
2026-001 | GEN011 | Dayton - Disclosure of Violation Form | N |  |  | N |  |  | N
2026-001 | GEN012 | KY - Protect My Kentucky Home Form | Y | MM | 2026-05-14 | Y | LV | 2026-04-30 | N
2026-001 | GEN013 | Note | Y | MM | 2026-05-01 | Y | LV | 2026-05-17 | N
2026-001 | GEN014 | Mortgage | Y | MM | 2026-04-21 | Y | LV | 2026-05-13 | N
2026-001 | GEN015 | Short-Form & Copy of Master Mortgage | N |  |  | N |  |  | N
2026-001 | GEN016 | Master Mortgage Reference | Y | MM | 2026-04-22 | N |  |  | N
2026-001 | GEN017 | Master Mortgage Acknowledgment | N |  |  | N |  |  | N
2026-001 | GEN018 | Names & marital status correct | N |  |  | N |  |  | N
2026-001 | GEN019 | Correct Legal Description Attached | N |  |  | N |  |  | N
2026-001 | GEN020 | Riders needed | N |  |  | N |  |  | N
2026-001 | CD001 | Buyer CD / Seller CD / SS | N |  |  | N |  |  | N
2026-001 | CD002 | SS & CD(s) numbers match | N |  |  | N |  |  | N
2026-001 | CD003 | Place of closing (HUD / SS) | Y | MM | 2026-04-29 | Y | LV | 2026-04-22 | N
2026-001 | CD004 | Payoffs | N |  |  | N |  |  | N
2026-001 | CD005 | All mortgages being paid off | N |  |  | N |  |  | N
2026-001 | CD006 | Enough interest being collected | Y | MM | 2026-05-01 | Y | LV | 2026-04-25 | N
2026-001 | CD007 | Earnest Money Credited Properly | Y | MM | 2026-04-28 | Y | LV | 2026-05-12 | N
2026-001 | CD008 | Tax Proration | N |  |  | N |  |  | N
2026-001 | CD009 | Property Taxes: Pay at closing? | N |  |  | N |  |  | N
2026-001 | CD010 | Bank Charges Included | N |  |  | N |  |  | N
2026-001 | CD011 | Title Insurance Premium | Y | MM | 2026-04-25 | N |  |  | N
2026-001 | CD012 | Refi / Reissue Rate | N |  |  | N |  |  | N
2026-001 | CD013 | Endorsements | Y | MM | 2026-05-12 | N |  |  | N
2026-001 | CD014 | Recording Fees (E-Record?) | N |  |  | N |  |  | N
2026-001 | CD015 | Transfer Fees | N |  |  | N |  |  | N
2026-001 | CD016 | Document Preparation Fee | N |  |  | N |  |  | N
2026-001 | CD017 | Commission | N |  |  | N |  |  | N
2026-001 | CD018 | KY Municipal Tax | Y | MM | 2026-04-30 | Y | LV | 2026-05-02 | N
2026-001 | CD019 | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | Y | MM | 2026-05-08 | Y | LV | 2026-05-18 | N
2026-001 | CD020 | Home Warranty | N |  |  | N |  |  | N
2026-001 | CD021 | Seller Paid Closing Costs | Y | MM | 2026-05-10 | Y | LV | 2026-05-04 | N
2026-001 | MISC001 | Title Issues - Resolved | Y | MM | 2026-05-13 | Y | LV | 2026-05-07 | N
2026-001 | MISC002 | Refinance - 3 day rescission? | N |  |  | N |  |  | N
2026-001 | MISC003 | Mortgage and Deed Names Match | N |  |  | N |  |  | N
2026-001 | MISC004 | Correct legal attached | N |  |  | N |  |  | N
2026-001 | MISC005 | KY - Preparer signature & Group Number | N |  |  | N |  |  | N
2026-001 | MISC006 | KY - Deed reference on mortgage | Y | MM | 2026-04-24 | N |  |  | N
2026-001 | MISC007 | IN - SSN statement on all recorded docs | N |  |  | N |  |  | N
2026-001 | MISC008 | OFAC List / SDN / Patriot Search | Y | MM | 2026-04-23 | Y | LV | 2026-04-24 | N
2026-001 | ST001 | Agreement Regarding Prorations | N |  |  | N |  |  | N
2026-001 | ST002 | Compliance Agreement | N |  |  | N |  |  | N
2026-001 | ST003 | Survey Affidavit | N |  |  | N |  |  | N
2026-001 | ST004 | Survey Acknowledgment | Y | MM | 2026-05-04 | Y | LV | 2026-05-06 | N
2026-001 | ST005 | Closing Affidavit | Y | MM | 2026-04-20 | Y | LV | 2026-05-11 | N
2026-001 | ST006 | Tax Indemnification | N |  |  | N |  |  | N
2026-001 | ST007 | Payoff Letter / Statement(s) | N |  |  | N |  |  | N
2026-001 | ST008 | Payoff Indemnification | N |  |  | N |  |  | N
2026-001 | ST009 | Privacy notice | Y | MM | 2026-04-23 | Y | LV | 2026-04-29 | N
2026-001 | ST010 | 1099 | N |  |  | N |  |  | N
2026-001 | ST011 | Owners' Title Ins. Notice | N |  |  | N |  |  | N
2026-001 | ST012 | 50 ways to lose your property | N |  |  | N |  |  | N
2026-001 | ST013 | Letter of Rep./Privity Disclaimer | N |  |  | N |  |  | N
2026-001 | ST014 | CPC Notice/Offer (OH-24.1 - 2 pages) | Y | MM | 2026-04-25 | Y | LV | 2026-05-06 | N
2026-001 | ST015 | Notice to Consumer re: mtg loan | N |  |  | N |  |  | N
2026-001 | ST016 | Closing Notice to Borrower | N |  |  | N |  |  | N
2026-001 | ST017 | Disbursement Instructions | Y | MM | 2026-05-09 | Y | LV | 2026-04-26 | N
2026-001 | ST018 | Unsecured Debt Indemnification | Y | MM | 2026-05-07 | N |  |  | N
2026-001 | ST019 | Not Me Affidavit | N |  |  | N |  |  | N
2026-001 | ST020 | Memorandum of Trust | N |  |  | N |  |  | N
2026-001 | ST021 | LLC Resolution | N |  |  | N |  |  | N
2026-001 | ST022 | Add'l Doc #1 | N |  |  | N |  |  | N
2026-001 | ST023 | Add'l Doc #2 | N |  |  | N |  |  | N
2026-001 | FIN001 | Numbers balance with Lender | Y | MM | 2026-05-15 | Y | LV | 2026-04-29 | N
2026-001 | FIN002 | Changed Docs to Kemba/EFCU | Y | MM | 2026-05-08 | Y | LV | 2026-05-20 | N
2026-001 | FIN003 | SS sent to agents | Y | MM | 2026-04-22 | N |  |  | N
2026-001 | FIN004 | Copies | N |  |  | N |  |  | N
2026-001 | FIN005 | Checks | N |  |  | N |  |  | N
2026-001 | POST001 | HUD | Y | MM | 2026-05-07 | Y | LV | 2026-04-25 | N
2026-001 | POST002 | Deed | Y | MM | 2026-05-03 | N |  |  | N
2026-001 | POST003 | Mortgage | N |  |  | N |  |  | N
2026-001 | POST004 | Note | N |  |  | N |  |  | N
2026-001 | POST005 | Subordination | N |  |  | N |  |  | N
2026-001 | POST006 | Notice of RTC | N |  |  | N |  |  | N
2026-001 | POST007 | Tax ID on 1099/Closing Affidavit | N |  |  | N |  |  | N
2026-001 | POST008 | Copies of drivers licenses | Y | MM | 2026-05-01 | Y | LV | 2026-05-04 | N
2026-001 | POST009 | Funds: Buyer / Lender / Seller | N |  |  | N |  |  | N
2026-001 | POST010 | Satisfaction | N |  |  | N |  |  | N
2026-001 | POST011 | Memorandum of Trust | Y | MM | 2026-04-20 | Y | LV | 2026-05-08 | N
2026-001 | POST012 | Power of Attorney | N |  |  | N |  |  | N
2026-001 | POST013 | Other | N |  |  | N |  |  | N
2026-002 | GEN001 | Title Commitment / Opinion Letter | Y | MM | 2026-05-07 | N |  |  | N
2026-002 | GEN002 | Title Update Needed/Requested | Y | MM | 2026-05-16 | N |  |  | N
2026-002 | GEN003 | Title Update Received | Y | MM | 2026-05-27 | Y | LV | 2026-05-21 | N
2026-002 | GEN004 | Proof of insurance | Y | MM | 2026-05-24 | Y | LV | 2026-05-24 | N
2026-002 | GEN005 | Survey | N |  |  | N |  |  | N
2026-002 | GEN006 | Deed | N |  |  | N |  |  | N
2026-002 | GEN007 | Ohio - Conveyance Statement | N |  |  | N |  |  | N
2026-002 | GEN008 | CPC Letter | Y | MM | 2026-05-19 | Y | LV | 2026-05-17 | N
2026-002 | GEN009 | Indiana Sales Disclosure Form | N |  |  | N |  |  | N
2026-002 | GEN010 | Indiana State Form 51781 (Yellow) | N |  |  | N |  |  | N
2026-002 | GEN011 | Dayton - Disclosure of Violation Form | N |  |  | N |  |  | N
2026-002 | GEN012 | KY - Protect My Kentucky Home Form | N |  |  | N |  |  | N
2026-002 | GEN013 | Note | N |  |  | N |  |  | N
2026-002 | GEN014 | Mortgage | Y | MM | 2026-05-16 | Y | LV | 2026-05-31 | N
2026-002 | GEN015 | Short-Form & Copy of Master Mortgage | N |  |  | N |  |  | N
2026-002 | GEN016 | Master Mortgage Reference | Y | MM | 2026-05-20 | Y | LV | 2026-05-10 | N
2026-002 | GEN017 | Master Mortgage Acknowledgment | N |  |  | N |  |  | N
2026-002 | GEN018 | Names & marital status correct | Y | MM | 2026-05-08 | Y | LV | 2026-05-20 | N
2026-002 | GEN019 | Correct Legal Description Attached | N |  |  | N |  |  | N
2026-002 | GEN020 | Riders needed | N |  |  | N |  |  | N
2026-002 | CD001 | Buyer CD / Seller CD / SS | Y | MM | 2026-05-23 | Y | LV | 2026-06-01 | N
2026-002 | CD002 | SS & CD(s) numbers match | Y | MM | 2026-05-30 | Y | LV | 2026-06-02 | N
2026-002 | CD003 | Place of closing (HUD / SS) | Y | MM | 2026-05-21 | Y | LV | 2026-05-12 | N
2026-002 | CD004 | Payoffs | N |  |  | N |  |  | N
2026-002 | CD005 | All mortgages being paid off | N |  |  | N |  |  | N
2026-002 | CD006 | Enough interest being collected | Y | MM | 2026-05-18 | Y | LV | 2026-05-14 | N
2026-002 | CD007 | Earnest Money Credited Properly | N |  |  | N |  |  | N
2026-002 | CD008 | Tax Proration | N |  |  | N |  |  | N
2026-002 | CD009 | Property Taxes: Pay at closing? | Y | MM | 2026-05-29 | Y | LV | 2026-05-31 | N
2026-002 | CD010 | Bank Charges Included | N |  |  | N |  |  | N
2026-002 | CD011 | Title Insurance Premium | N |  |  | N |  |  | N
2026-002 | CD012 | Refi / Reissue Rate | Y | MM | 2026-05-07 | Y | LV | 2026-05-24 | N
2026-002 | CD013 | Endorsements | N |  |  | N |  |  | N
2026-002 | CD014 | Recording Fees (E-Record?) | Y | MM | 2026-05-07 | Y | LV | 2026-05-24 | N
2026-002 | CD015 | Transfer Fees | N |  |  | N |  |  | N
2026-002 | CD016 | Document Preparation Fee | N |  |  | N |  |  | N
2026-002 | CD017 | Commission | N |  |  | N |  |  | N
2026-002 | CD018 | KY Municipal Tax | Y | MM | 2026-05-11 | Y | LV | 2026-05-08 | N
2026-002 | CD019 | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | N |  |  | N |  |  | N
2026-002 | CD020 | Home Warranty | N |  |  | N |  |  | N
2026-002 | CD021 | Seller Paid Closing Costs | Y | MM | 2026-05-24 | Y | LV | 2026-05-13 | N
2026-002 | MISC001 | Title Issues - Resolved | N |  |  | N |  |  | N
2026-002 | MISC002 | Refinance - 3 day rescission? | Y | MM | 2026-05-27 | Y | LV | 2026-05-24 | N
2026-002 | MISC003 | Mortgage and Deed Names Match | N |  |  | N |  |  | N
2026-002 | MISC004 | Correct legal attached | Y | MM | 2026-05-27 | Y | LV | 2026-05-28 | N
2026-002 | MISC005 | KY - Preparer signature & Group Number | Y | MM | 2026-05-10 | Y | LV | 2026-05-27 | N
2026-002 | MISC006 | KY - Deed reference on mortgage | N |  |  | N |  |  | N
2026-002 | MISC007 | IN - SSN statement on all recorded docs | N |  |  | N |  |  | N
2026-002 | MISC008 | OFAC List / SDN / Patriot Search | N |  |  | N |  |  | N
2026-002 | ST001 | Agreement Regarding Prorations | N |  |  | N |  |  | N
2026-002 | ST002 | Compliance Agreement | Y | MM | 2026-05-24 | Y | LV | 2026-05-09 | N
2026-002 | ST003 | Survey Affidavit | Y | MM | 2026-05-14 | Y | LV | 2026-05-10 | N
2026-002 | ST004 | Survey Acknowledgment | N |  |  | N |  |  | N
2026-002 | ST005 | Closing Affidavit | N |  |  | N |  |  | N
2026-002 | ST006 | Tax Indemnification | N |  |  | N |  |  | N
2026-002 | ST007 | Payoff Letter / Statement(s) | Y | MM | 2026-05-23 | Y | LV | 2026-05-28 | N
2026-002 | ST008 | Payoff Indemnification | Y | MM | 2026-05-31 | N |  |  | N
2026-002 | ST009 | Privacy notice | N |  |  | N |  |  | N
2026-002 | ST010 | 1099 | Y | MM | 2026-05-15 | N |  |  | N
2026-002 | ST011 | Owners' Title Ins. Notice | N |  |  | N |  |  | N
2026-002 | ST012 | 50 ways to lose your property | Y | MM | 2026-05-14 | N |  |  | N
2026-002 | ST013 | Letter of Rep./Privity Disclaimer | Y | MM | 2026-05-23 | Y | LV | 2026-05-10 | N
2026-002 | ST014 | CPC Notice/Offer (OH-24.1 - 2 pages) | Y | MM | 2026-05-28 | Y | LV | 2026-05-16 | N
2026-002 | ST015 | Notice to Consumer re: mtg loan | Y | MM | 2026-05-14 | Y | LV | 2026-05-22 | N
2026-002 | ST016 | Closing Notice to Borrower | N |  |  | N |  |  | N
2026-002 | ST017 | Disbursement Instructions | N |  |  | N |  |  | N
2026-002 | ST018 | Unsecured Debt Indemnification | N |  |  | N |  |  | N
2026-002 | ST019 | Not Me Affidavit | Y | MM | 2026-05-14 | Y | LV | 2026-05-07 | N
2026-002 | ST020 | Memorandum of Trust | Y | MM | 2026-05-26 | N |  |  | N
2026-002 | ST021 | LLC Resolution | N |  |  | N |  |  | N
2026-002 | ST022 | Add'l Doc #1 | Y | MM | 2026-05-28 | Y | LV | 2026-05-19 | N
2026-002 | ST023 | Add'l Doc #2 | N |  |  | N |  |  | N
2026-002 | FIN001 | Numbers balance with Lender | Y | MM | 2026-05-28 | N |  |  | N
2026-002 | FIN002 | Changed Docs to Kemba/EFCU | N |  |  | N |  |  | N
2026-002 | FIN003 | SS sent to agents | N |  |  | N |  |  | N
2026-002 | FIN004 | Copies | N |  |  | N |  |  | N
2026-002 | FIN005 | Checks | N |  |  | N |  |  | N
2026-002 | POST001 | HUD | Y | MM | 2026-05-15 | Y | LV | 2026-05-17 | N
2026-002 | POST002 | Deed | N |  |  | N |  |  | N
2026-002 | POST003 | Mortgage | N |  |  | N |  |  | N
2026-002 | POST004 | Note | N |  |  | N |  |  | N
2026-002 | POST005 | Subordination | N |  |  | N |  |  | N
2026-002 | POST006 | Notice of RTC | Y | MM | 2026-05-09 | Y | LV | 2026-05-17 | N
2026-002 | POST007 | Tax ID on 1099/Closing Affidavit | N |  |  | N |  |  | N
2026-002 | POST008 | Copies of drivers licenses | N |  |  | N |  |  | N
2026-002 | POST009 | Funds: Buyer / Lender / Seller | N |  |  | N |  |  | N
2026-002 | POST010 | Satisfaction | N |  |  | N |  |  | N
2026-002 | POST011 | Memorandum of Trust | Y | MM | 2026-05-11 | N |  |  | N
2026-002 | POST012 | Power of Attorney | N |  |  | N |  |  | N
2026-002 | POST013 | Other | N |  |  | N |  |  | N
2026-003 | GEN001 | Title Commitment / Opinion Letter | N |  |  | N |  |  | N
2026-003 | GEN002 | Title Update Needed/Requested | N |  |  | N |  |  | N
2026-003 | GEN003 | Title Update Received | N |  |  | N |  |  | N
2026-003 | GEN004 | Proof of insurance | N |  |  | N |  |  | N
2026-003 | GEN005 | Survey | N |  |  | N |  |  | N
2026-003 | GEN006 | Deed | N |  |  | N |  |  | N
2026-003 | GEN007 | Ohio - Conveyance Statement | N |  |  | N |  |  | N
2026-003 | GEN008 | CPC Letter | N |  |  | N |  |  | N
2026-003 | GEN009 | Indiana Sales Disclosure Form | N |  |  | N |  |  | N
2026-003 | GEN010 | Indiana State Form 51781 (Yellow) | N |  |  | N |  |  | N
2026-003 | GEN011 | Dayton - Disclosure of Violation Form | N |  |  | N |  |  | N
2026-003 | GEN012 | KY - Protect My Kentucky Home Form | N |  |  | N |  |  | N
2026-003 | GEN013 | Note | N |  |  | N |  |  | N
2026-003 | GEN014 | Mortgage | N |  |  | N |  |  | N
2026-003 | GEN015 | Short-Form & Copy of Master Mortgage | N |  |  | N |  |  | N
2026-003 | GEN016 | Master Mortgage Reference | N |  |  | N |  |  | N
2026-003 | GEN017 | Master Mortgage Acknowledgment | N |  |  | N |  |  | N
2026-003 | GEN018 | Names & marital status correct | N |  |  | N |  |  | N
2026-003 | GEN019 | Correct Legal Description Attached | N |  |  | N |  |  | N
2026-003 | GEN020 | Riders needed | N |  |  | N |  |  | N
2026-003 | CD001 | Buyer CD / Seller CD / SS | N |  |  | N |  |  | N
2026-003 | CD002 | SS & CD(s) numbers match | N |  |  | N |  |  | N
2026-003 | CD003 | Place of closing (HUD / SS) | N |  |  | N |  |  | N
2026-003 | CD004 | Payoffs | N |  |  | N |  |  | N
2026-003 | CD005 | All mortgages being paid off | N |  |  | N |  |  | N
2026-003 | CD006 | Enough interest being collected | N |  |  | N |  |  | N
2026-003 | CD007 | Earnest Money Credited Properly | N |  |  | N |  |  | N
2026-003 | CD008 | Tax Proration | N |  |  | N |  |  | N
2026-003 | CD009 | Property Taxes: Pay at closing? | N |  |  | N |  |  | N
2026-003 | CD010 | Bank Charges Included | N |  |  | N |  |  | N
2026-003 | CD011 | Title Insurance Premium | N |  |  | N |  |  | N
2026-003 | CD012 | Refi / Reissue Rate | N |  |  | N |  |  | N
2026-003 | CD013 | Endorsements | N |  |  | N |  |  | N
2026-003 | CD014 | Recording Fees (E-Record?) | N |  |  | N |  |  | N
2026-003 | CD015 | Transfer Fees | N |  |  | N |  |  | N
2026-003 | CD016 | Document Preparation Fee | N |  |  | N |  |  | N
2026-003 | CD017 | Commission | N |  |  | N |  |  | N
2026-003 | CD018 | KY Municipal Tax | N |  |  | N |  |  | N
2026-003 | CD019 | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | N |  |  | N |  |  | N
2026-003 | CD020 | Home Warranty | N |  |  | N |  |  | N
2026-003 | CD021 | Seller Paid Closing Costs | N |  |  | N |  |  | N
2026-003 | MISC001 | Title Issues - Resolved | N |  |  | N |  |  | N
2026-003 | MISC002 | Refinance - 3 day rescission? | N |  |  | N |  |  | N
2026-003 | MISC003 | Mortgage and Deed Names Match | N |  |  | N |  |  | N
2026-003 | MISC004 | Correct legal attached | N |  |  | N |  |  | N
2026-003 | MISC005 | KY - Preparer signature & Group Number | N |  |  | N |  |  | N
2026-003 | MISC006 | KY - Deed reference on mortgage | N |  |  | N |  |  | N
2026-003 | MISC007 | IN - SSN statement on all recorded docs | N |  |  | N |  |  | N
2026-003 | MISC008 | OFAC List / SDN / Patriot Search | N |  |  | N |  |  | N
2026-003 | ST001 | Agreement Regarding Prorations | N |  |  | N |  |  | N
2026-003 | ST002 | Compliance Agreement | N |  |  | N |  |  | N
2026-003 | ST003 | Survey Affidavit | N |  |  | N |  |  | N
2026-003 | ST004 | Survey Acknowledgment | N |  |  | N |  |  | N
2026-003 | ST005 | Closing Affidavit | N |  |  | N |  |  | N
2026-003 | ST006 | Tax Indemnification | N |  |  | N |  |  | N
2026-003 | ST007 | Payoff Letter / Statement(s) | N |  |  | N |  |  | N
2026-003 | ST008 | Payoff Indemnification | N |  |  | N |  |  | N
2026-003 | ST009 | Privacy notice | N |  |  | N |  |  | N
2026-003 | ST010 | 1099 | N |  |  | N |  |  | N
2026-003 | ST011 | Owners' Title Ins. Notice | N |  |  | N |  |  | N
2026-003 | ST012 | 50 ways to lose your property | N |  |  | N |  |  | N
2026-003 | ST013 | Letter of Rep./Privity Disclaimer | N |  |  | N |  |  | N
2026-003 | ST014 | CPC Notice/Offer (OH-24.1 - 2 pages) | N |  |  | N |  |  | N
2026-003 | ST015 | Notice to Consumer re: mtg loan | N |  |  | N |  |  | N
2026-003 | ST016 | Closing Notice to Borrower | N |  |  | N |  |  | N
2026-003 | ST017 | Disbursement Instructions | N |  |  | N |  |  | N
2026-003 | ST018 | Unsecured Debt Indemnification | N |  |  | N |  |  | N
2026-003 | ST019 | Not Me Affidavit | N |  |  | N |  |  | N
2026-003 | ST020 | Memorandum of Trust | N |  |  | N |  |  | N
2026-003 | ST021 | LLC Resolution | N |  |  | N |  |  | N
2026-003 | ST022 | Add'l Doc #1 | N |  |  | N |  |  | N
2026-003 | ST023 | Add'l Doc #2 | N |  |  | N |  |  | N
2026-003 | FIN001 | Numbers balance with Lender | N |  |  | N |  |  | N
2026-003 | FIN002 | Changed Docs to Kemba/EFCU | N |  |  | N |  |  | N
2026-003 | FIN003 | SS sent to agents | N |  |  | N |  |  | N
2026-003 | FIN004 | Copies | N |  |  | N |  |  | N
2026-003 | FIN005 | Checks | N |  |  | N |  |  | N
2026-003 | POST001 | HUD | N |  |  | N |  |  | N
2026-003 | POST002 | Deed | N |  |  | N |  |  | N
2026-003 | POST003 | Mortgage | N |  |  | N |  |  | N
2026-003 | POST004 | Note | N |  |  | N |  |  | N
2026-003 | POST005 | Subordination | N |  |  | N |  |  | N
2026-003 | POST006 | Notice of RTC | N |  |  | N |  |  | N
2026-003 | POST007 | Tax ID on 1099/Closing Affidavit | N |  |  | N |  |  | N
2026-003 | POST008 | Copies of drivers licenses | N |  |  | N |  |  | N
2026-003 | POST009 | Funds: Buyer / Lender / Seller | N |  |  | N |  |  | N
2026-003 | POST010 | Satisfaction | N |  |  | N |  |  | N
2026-003 | POST011 | Memorandum of Trust | N |  |  | N |  |  | N
2026-003 | POST012 | Power of Attorney | N |  |  | N |  |  | N
2026-003 | POST013 | Other | N |  |  | N |  |  | N
2026-004 | GEN001 | Title Commitment / Opinion Letter | N |  |  | N |  |  | N
2026-004 | GEN002 | Title Update Needed/Requested | N |  |  | N |  |  | N
2026-004 | GEN003 | Title Update Received | N |  |  | N |  |  | N
2026-004 | GEN004 | Proof of insurance | N |  |  | N |  |  | N
2026-004 | GEN005 | Survey | N |  |  | N |  |  | N
2026-004 | GEN006 | Deed | N |  |  | N |  |  | N
2026-004 | GEN007 | Ohio - Conveyance Statement | N |  |  | N |  |  | N
2026-004 | GEN008 | CPC Letter | N |  |  | N |  |  | N
2026-004 | GEN009 | Indiana Sales Disclosure Form | N |  |  | N |  |  | N
2026-004 | GEN010 | Indiana State Form 51781 (Yellow) | N |  |  | N |  |  | N
2026-004 | GEN011 | Dayton - Disclosure of Violation Form | N |  |  | N |  |  | N
2026-004 | GEN012 | KY - Protect My Kentucky Home Form | N |  |  | N |  |  | N
2026-004 | GEN013 | Note | N |  |  | N |  |  | N
2026-004 | GEN014 | Mortgage | N |  |  | N |  |  | N
2026-004 | GEN015 | Short-Form & Copy of Master Mortgage | N |  |  | N |  |  | N
2026-004 | GEN016 | Master Mortgage Reference | N |  |  | N |  |  | N
2026-004 | GEN017 | Master Mortgage Acknowledgment | N |  |  | N |  |  | N
2026-004 | GEN018 | Names & marital status correct | N |  |  | N |  |  | N
2026-004 | GEN019 | Correct Legal Description Attached | N |  |  | N |  |  | N
2026-004 | GEN020 | Riders needed | N |  |  | N |  |  | N
2026-004 | CD001 | Buyer CD / Seller CD / SS | N |  |  | N |  |  | N
2026-004 | CD002 | SS & CD(s) numbers match | N |  |  | N |  |  | N
2026-004 | CD003 | Place of closing (HUD / SS) | N |  |  | N |  |  | N
2026-004 | CD004 | Payoffs | N |  |  | N |  |  | N
2026-004 | CD005 | All mortgages being paid off | N |  |  | N |  |  | N
2026-004 | CD006 | Enough interest being collected | N |  |  | N |  |  | N
2026-004 | CD007 | Earnest Money Credited Properly | N |  |  | N |  |  | N
2026-004 | CD008 | Tax Proration | N |  |  | N |  |  | N
2026-004 | CD009 | Property Taxes: Pay at closing? | N |  |  | N |  |  | N
2026-004 | CD010 | Bank Charges Included | N |  |  | N |  |  | N
2026-004 | CD011 | Title Insurance Premium | N |  |  | N |  |  | N
2026-004 | CD012 | Refi / Reissue Rate | N |  |  | N |  |  | N
2026-004 | CD013 | Endorsements | N |  |  | N |  |  | N
2026-004 | CD014 | Recording Fees (E-Record?) | N |  |  | N |  |  | N
2026-004 | CD015 | Transfer Fees | N |  |  | N |  |  | N
2026-004 | CD016 | Document Preparation Fee | N |  |  | N |  |  | N
2026-004 | CD017 | Commission | N |  |  | N |  |  | N
2026-004 | CD018 | KY Municipal Tax | N |  |  | N |  |  | N
2026-004 | CD019 | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | N |  |  | N |  |  | N
2026-004 | CD020 | Home Warranty | N |  |  | N |  |  | N
2026-004 | CD021 | Seller Paid Closing Costs | N |  |  | N |  |  | N
2026-004 | MISC001 | Title Issues - Resolved | N |  |  | N |  |  | N
2026-004 | MISC002 | Refinance - 3 day rescission? | N |  |  | N |  |  | N
2026-004 | MISC003 | Mortgage and Deed Names Match | N |  |  | N |  |  | N
2026-004 | MISC004 | Correct legal attached | N |  |  | N |  |  | N
2026-004 | MISC005 | KY - Preparer signature & Group Number | N |  |  | N |  |  | N
2026-004 | MISC006 | KY - Deed reference on mortgage | N |  |  | N |  |  | N
2026-004 | MISC007 | IN - SSN statement on all recorded docs | N |  |  | N |  |  | N
2026-004 | MISC008 | OFAC List / SDN / Patriot Search | N |  |  | N |  |  | N
2026-004 | ST001 | Agreement Regarding Prorations | N |  |  | N |  |  | N
2026-004 | ST002 | Compliance Agreement | N |  |  | N |  |  | N
2026-004 | ST003 | Survey Affidavit | N |  |  | N |  |  | N
2026-004 | ST004 | Survey Acknowledgment | N |  |  | N |  |  | N
2026-004 | ST005 | Closing Affidavit | N |  |  | N |  |  | N
2026-004 | ST006 | Tax Indemnification | N |  |  | N |  |  | N
2026-004 | ST007 | Payoff Letter / Statement(s) | N |  |  | N |  |  | N
2026-004 | ST008 | Payoff Indemnification | N |  |  | N |  |  | N
2026-004 | ST009 | Privacy notice | N |  |  | N |  |  | N
2026-004 | ST010 | 1099 | N |  |  | N |  |  | N
2026-004 | ST011 | Owners' Title Ins. Notice | N |  |  | N |  |  | N
2026-004 | ST012 | 50 ways to lose your property | N |  |  | N |  |  | N
2026-004 | ST013 | Letter of Rep./Privity Disclaimer | N |  |  | N |  |  | N
2026-004 | ST014 | CPC Notice/Offer (OH-24.1 - 2 pages) | N |  |  | N |  |  | N
2026-004 | ST015 | Notice to Consumer re: mtg loan | N |  |  | N |  |  | N
2026-004 | ST016 | Closing Notice to Borrower | N |  |  | N |  |  | N
2026-004 | ST017 | Disbursement Instructions | N |  |  | N |  |  | N
2026-004 | ST018 | Unsecured Debt Indemnification | N |  |  | N |  |  | N
2026-004 | ST019 | Not Me Affidavit | N |  |  | N |  |  | N
2026-004 | ST020 | Memorandum of Trust | N |  |  | N |  |  | N
2026-004 | ST021 | LLC Resolution | N |  |  | N |  |  | N
2026-004 | ST022 | Add'l Doc #1 | N |  |  | N |  |  | N
2026-004 | ST023 | Add'l Doc #2 | N |  |  | N |  |  | N
2026-004 | FIN001 | Numbers balance with Lender | N |  |  | N |  |  | N
2026-004 | FIN002 | Changed Docs to Kemba/EFCU | N |  |  | N |  |  | N
2026-004 | FIN003 | SS sent to agents | N |  |  | N |  |  | N
2026-004 | FIN004 | Copies | N |  |  | N |  |  | N
2026-004 | FIN005 | Checks | N |  |  | N |  |  | N
2026-004 | POST001 | HUD | N |  |  | N |  |  | N
2026-004 | POST002 | Deed | N |  |  | N |  |  | N
2026-004 | POST003 | Mortgage | N |  |  | N |  |  | N
2026-004 | POST004 | Note | N |  |  | N |  |  | N
2026-004 | POST005 | Subordination | N |  |  | N |  |  | N
2026-004 | POST006 | Notice of RTC | N |  |  | N |  |  | N
2026-004 | POST007 | Tax ID on 1099/Closing Affidavit | N |  |  | N |  |  | N
2026-004 | POST008 | Copies of drivers licenses | N |  |  | N |  |  | N
2026-004 | POST009 | Funds: Buyer / Lender / Seller | N |  |  | N |  |  | N
2026-004 | POST010 | Satisfaction | N |  |  | N |  |  | N
2026-004 | POST011 | Memorandum of Trust | N |  |  | N |  |  | N
2026-004 | POST012 | Power of Attorney | N |  |  | N |  |  | N
2026-004 | POST013 | Other | N |  |  | N |  |  | N
2026-005 | GEN001 | Title Commitment / Opinion Letter | N |  |  | N |  |  | N
2026-005 | GEN002 | Title Update Needed/Requested | N |  |  | N |  |  | N
2026-005 | GEN003 | Title Update Received | N |  |  | N |  |  | N
2026-005 | GEN004 | Proof of insurance | N |  |  | N |  |  | N
2026-005 | GEN005 | Survey | N |  |  | N |  |  | N
2026-005 | GEN006 | Deed | N |  |  | N |  |  | N
2026-005 | GEN007 | Ohio - Conveyance Statement | N |  |  | N |  |  | N
2026-005 | GEN008 | CPC Letter | N |  |  | N |  |  | N
2026-005 | GEN009 | Indiana Sales Disclosure Form | N |  |  | N |  |  | N
2026-005 | GEN010 | Indiana State Form 51781 (Yellow) | N |  |  | N |  |  | N
2026-005 | GEN011 | Dayton - Disclosure of Violation Form | N |  |  | N |  |  | N
2026-005 | GEN012 | KY - Protect My Kentucky Home Form | N |  |  | N |  |  | N
2026-005 | GEN013 | Note | N |  |  | N |  |  | N
2026-005 | GEN014 | Mortgage | N |  |  | N |  |  | N
2026-005 | GEN015 | Short-Form & Copy of Master Mortgage | N |  |  | N |  |  | N
2026-005 | GEN016 | Master Mortgage Reference | N |  |  | N |  |  | N
2026-005 | GEN017 | Master Mortgage Acknowledgment | N |  |  | N |  |  | N
2026-005 | GEN018 | Names & marital status correct | N |  |  | N |  |  | N
2026-005 | GEN019 | Correct Legal Description Attached | N |  |  | N |  |  | N
2026-005 | GEN020 | Riders needed | N |  |  | N |  |  | N
2026-005 | CD001 | Buyer CD / Seller CD / SS | N |  |  | N |  |  | N
2026-005 | CD002 | SS & CD(s) numbers match | N |  |  | N |  |  | N
2026-005 | CD003 | Place of closing (HUD / SS) | N |  |  | N |  |  | N
2026-005 | CD004 | Payoffs | N |  |  | N |  |  | N
2026-005 | CD005 | All mortgages being paid off | N |  |  | N |  |  | N
2026-005 | CD006 | Enough interest being collected | N |  |  | N |  |  | N
2026-005 | CD007 | Earnest Money Credited Properly | N |  |  | N |  |  | N
2026-005 | CD008 | Tax Proration | N |  |  | N |  |  | N
2026-005 | CD009 | Property Taxes: Pay at closing? | N |  |  | N |  |  | N
2026-005 | CD010 | Bank Charges Included | N |  |  | N |  |  | N
2026-005 | CD011 | Title Insurance Premium | N |  |  | N |  |  | N
2026-005 | CD012 | Refi / Reissue Rate | N |  |  | N |  |  | N
2026-005 | CD013 | Endorsements | N |  |  | N |  |  | N
2026-005 | CD014 | Recording Fees (E-Record?) | N |  |  | N |  |  | N
2026-005 | CD015 | Transfer Fees | N |  |  | N |  |  | N
2026-005 | CD016 | Document Preparation Fee | N |  |  | N |  |  | N
2026-005 | CD017 | Commission | N |  |  | N |  |  | N
2026-005 | CD018 | KY Municipal Tax | N |  |  | N |  |  | N
2026-005 | CD019 | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | N |  |  | N |  |  | N
2026-005 | CD020 | Home Warranty | N |  |  | N |  |  | N
2026-005 | CD021 | Seller Paid Closing Costs | N |  |  | N |  |  | N
2026-005 | MISC001 | Title Issues - Resolved | N |  |  | N |  |  | N
2026-005 | MISC002 | Refinance - 3 day rescission? | N |  |  | N |  |  | N
2026-005 | MISC003 | Mortgage and Deed Names Match | N |  |  | N |  |  | N
2026-005 | MISC004 | Correct legal attached | N |  |  | N |  |  | N
2026-005 | MISC005 | KY - Preparer signature & Group Number | N |  |  | N |  |  | N
2026-005 | MISC006 | KY - Deed reference on mortgage | N |  |  | N |  |  | N
2026-005 | MISC007 | IN - SSN statement on all recorded docs | N |  |  | N |  |  | N
2026-005 | MISC008 | OFAC List / SDN / Patriot Search | N |  |  | N |  |  | N
2026-005 | ST001 | Agreement Regarding Prorations | N |  |  | N |  |  | N
2026-005 | ST002 | Compliance Agreement | N |  |  | N |  |  | N
2026-005 | ST003 | Survey Affidavit | N |  |  | N |  |  | N
2026-005 | ST004 | Survey Acknowledgment | N |  |  | N |  |  | N
2026-005 | ST005 | Closing Affidavit | N |  |  | N |  |  | N
2026-005 | ST006 | Tax Indemnification | N |  |  | N |  |  | N
2026-005 | ST007 | Payoff Letter / Statement(s) | N |  |  | N |  |  | N
2026-005 | ST008 | Payoff Indemnification | N |  |  | N |  |  | N
2026-005 | ST009 | Privacy notice | N |  |  | N |  |  | N
2026-005 | ST010 | 1099 | N |  |  | N |  |  | N
2026-005 | ST011 | Owners' Title Ins. Notice | N |  |  | N |  |  | N
2026-005 | ST012 | 50 ways to lose your property | N |  |  | N |  |  | N
2026-005 | ST013 | Letter of Rep./Privity Disclaimer | N |  |  | N |  |  | N
2026-005 | ST014 | CPC Notice/Offer (OH-24.1 - 2 pages) | N |  |  | N |  |  | N
2026-005 | ST015 | Notice to Consumer re: mtg loan | N |  |  | N |  |  | N
2026-005 | ST016 | Closing Notice to Borrower | N |  |  | N |  |  | N
2026-005 | ST017 | Disbursement Instructions | N |  |  | N |  |  | N
2026-005 | ST018 | Unsecured Debt Indemnification | N |  |  | N |  |  | N
2026-005 | ST019 | Not Me Affidavit | N |  |  | N |  |  | N
2026-005 | ST020 | Memorandum of Trust | N |  |  | N |  |  | N
2026-005 | ST021 | LLC Resolution | N |  |  | N |  |  | N
2026-005 | ST022 | Add'l Doc #1 | N |  |  | N |  |  | N
2026-005 | ST023 | Add'l Doc #2 | N |  |  | N |  |  | N
2026-005 | FIN001 | Numbers balance with Lender | N |  |  | N |  |  | N
2026-005 | FIN002 | Changed Docs to Kemba/EFCU | N |  |  | N |  |  | N
2026-005 | FIN003 | SS sent to agents | N |  |  | N |  |  | N
2026-005 | FIN004 | Copies | N |  |  | N |  |  | N
2026-005 | FIN005 | Checks | N |  |  | N |  |  | N
2026-005 | POST001 | HUD | N |  |  | N |  |  | N
2026-005 | POST002 | Deed | N |  |  | N |  |  | N
2026-005 | POST003 | Mortgage | N |  |  | N |  |  | N
2026-005 | POST004 | Note | N |  |  | N |  |  | N
2026-005 | POST005 | Subordination | N |  |  | N |  |  | N
2026-005 | POST006 | Notice of RTC | N |  |  | N |  |  | N
2026-005 | POST007 | Tax ID on 1099/Closing Affidavit | N |  |  | N |  |  | N
2026-005 | POST008 | Copies of drivers licenses | N |  |  | N |  |  | N
2026-005 | POST009 | Funds: Buyer / Lender / Seller | N |  |  | N |  |  | N
2026-005 | POST010 | Satisfaction | N |  |  | N |  |  | N
2026-005 | POST011 | Memorandum of Trust | N |  |  | N |  |  | N
2026-005 | POST012 | Power of Attorney | N |  |  | N |  |  | N
2026-005 | POST013 | Other | N |  |  | N |  |  | N
2026-006 | GEN001 | Title Commitment / Opinion Letter | Y | MM | 2026-02-28 | Y | LV | 2026-02-15 | N
2026-006 | GEN002 | Title Update Needed/Requested | Y | MM | 2026-02-20 | Y | LV | 2026-03-10 | N
2026-006 | GEN003 | Title Update Received | Y | MM | 2026-02-25 | Y | LV | 2026-03-12 | N
2026-006 | GEN004 | Proof of insurance | Y | MM | 2026-02-28 | Y | LV | 2026-03-12 | N
2026-006 | GEN005 | Survey | Y | MM | 2026-03-08 | Y | LV | 2026-03-14 | N
2026-006 | GEN006 | Deed | Y | MM | 2026-03-10 | Y | LV | 2026-03-12 | N
2026-006 | GEN007 | Ohio - Conveyance Statement | Y | MM | 2026-02-22 | Y | LV | 2026-02-23 | N
2026-006 | GEN008 | CPC Letter | Y | MM | 2026-02-20 | Y | LV | 2026-03-12 | N
2026-006 | GEN009 | Indiana Sales Disclosure Form | Y | MM | 2026-03-09 | Y | LV | 2026-02-18 | N
2026-006 | GEN010 | Indiana State Form 51781 (Yellow) | Y | MM | 2026-02-27 | Y | LV | 2026-03-14 | N
2026-006 | GEN011 | Dayton - Disclosure of Violation Form | Y | MM | 2026-02-16 | Y | LV | 2026-03-14 | N
2026-006 | GEN012 | KY - Protect My Kentucky Home Form | Y | MM | 2026-03-02 | Y | LV | 2026-02-22 | N
2026-006 | GEN013 | Note | Y | MM | 2026-02-21 | Y | LV | 2026-03-13 | N
2026-006 | GEN014 | Mortgage | Y | MM | 2026-03-01 | Y | LV | 2026-02-26 | N
2026-006 | GEN015 | Short-Form & Copy of Master Mortgage | Y | MM | 2026-02-24 | Y | LV | 2026-03-13 | N
2026-006 | GEN016 | Master Mortgage Reference | Y | MM | 2026-03-12 | Y | LV | 2026-03-14 | N
2026-006 | GEN017 | Master Mortgage Acknowledgment | Y | MM | 2026-02-22 | Y | LV | 2026-02-22 | N
2026-006 | GEN018 | Names & marital status correct | Y | MM | 2026-02-15 | Y | LV | 2026-03-08 | N
2026-006 | GEN019 | Correct Legal Description Attached | Y | MM | 2026-02-21 | Y | LV | 2026-02-27 | N
2026-006 | GEN020 | Riders needed | Y | MM | 2026-02-25 | Y | LV | 2026-02-23 | N
2026-006 | CD001 | Buyer CD / Seller CD / SS | Y | MM | 2026-02-17 | Y | LV | 2026-03-17 | N
2026-006 | CD002 | SS & CD(s) numbers match | Y | MM | 2026-03-11 | Y | LV | 2026-02-23 | N
2026-006 | CD003 | Place of closing (HUD / SS) | Y | MM | 2026-02-26 | Y | LV | 2026-03-07 | N
2026-006 | CD004 | Payoffs | Y | MM | 2026-03-03 | Y | LV | 2026-02-27 | N
2026-006 | CD005 | All mortgages being paid off | Y | MM | 2026-03-08 | Y | LV | 2026-03-13 | N
2026-006 | CD006 | Enough interest being collected | Y | MM | 2026-03-04 | Y | LV | 2026-02-25 | N
2026-006 | CD007 | Earnest Money Credited Properly | Y | MM | 2026-02-15 | Y | LV | 2026-02-18 | N
2026-006 | CD008 | Tax Proration | Y | MM | 2026-02-23 | Y | LV | 2026-02-20 | N
2026-006 | CD009 | Property Taxes: Pay at closing? | Y | MM | 2026-03-05 | Y | LV | 2026-03-17 | N
2026-006 | CD010 | Bank Charges Included | Y | MM | 2026-02-23 | Y | LV | 2026-02-16 | N
2026-006 | CD011 | Title Insurance Premium | Y | MM | 2026-02-18 | Y | LV | 2026-03-06 | N
2026-006 | CD012 | Refi / Reissue Rate | Y | MM | 2026-02-28 | Y | LV | 2026-02-26 | N
2026-006 | CD013 | Endorsements | Y | MM | 2026-03-10 | Y | LV | 2026-03-12 | N
2026-006 | CD014 | Recording Fees (E-Record?) | Y | MM | 2026-02-25 | Y | LV | 2026-02-28 | N
2026-006 | CD015 | Transfer Fees | Y | MM | 2026-03-06 | Y | LV | 2026-03-03 | N
2026-006 | CD016 | Document Preparation Fee | Y | MM | 2026-02-18 | Y | LV | 2026-02-27 | N
2026-006 | CD017 | Commission | Y | MM | 2026-03-05 | Y | LV | 2026-02-21 | N
2026-006 | CD018 | KY Municipal Tax | Y | MM | 2026-02-23 | Y | LV | 2026-02-16 | N
2026-006 | CD019 | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | Y | MM | 2026-03-09 | Y | LV | 2026-02-28 | N
2026-006 | CD020 | Home Warranty | Y | MM | 2026-02-15 | Y | LV | 2026-03-03 | N
2026-006 | CD021 | Seller Paid Closing Costs | Y | MM | 2026-03-12 | Y | LV | 2026-03-04 | N
2026-006 | MISC001 | Title Issues - Resolved | Y | MM | 2026-03-08 | Y | LV | 2026-03-10 | N
2026-006 | MISC002 | Refinance - 3 day rescission? | Y | MM | 2026-03-10 | Y | LV | 2026-03-10 | N
2026-006 | MISC003 | Mortgage and Deed Names Match | Y | MM | 2026-03-08 | Y | LV | 2026-02-21 | N
2026-006 | MISC004 | Correct legal attached | Y | MM | 2026-02-26 | Y | LV | 2026-02-28 | N
2026-006 | MISC005 | KY - Preparer signature & Group Number | Y | MM | 2026-02-17 | Y | LV | 2026-03-17 | N
2026-006 | MISC006 | KY - Deed reference on mortgage | Y | MM | 2026-03-08 | Y | LV | 2026-03-16 | N
2026-006 | MISC007 | IN - SSN statement on all recorded docs | Y | MM | 2026-02-25 | Y | LV | 2026-03-06 | N
2026-006 | MISC008 | OFAC List / SDN / Patriot Search | Y | MM | 2026-02-25 | Y | LV | 2026-03-08 | N
2026-006 | ST001 | Agreement Regarding Prorations | Y | MM | 2026-02-18 | Y | LV | 2026-03-10 | N
2026-006 | ST002 | Compliance Agreement | Y | MM | 2026-02-24 | Y | LV | 2026-03-03 | N
2026-006 | ST003 | Survey Affidavit | Y | MM | 2026-02-24 | Y | LV | 2026-03-08 | N
2026-006 | ST004 | Survey Acknowledgment | Y | MM | 2026-02-28 | Y | LV | 2026-02-25 | N
2026-006 | ST005 | Closing Affidavit | Y | MM | 2026-02-27 | Y | LV | 2026-03-09 | N
2026-006 | ST006 | Tax Indemnification | Y | MM | 2026-02-24 | Y | LV | 2026-03-04 | N
2026-006 | ST007 | Payoff Letter / Statement(s) | Y | MM | 2026-02-19 | Y | LV | 2026-02-21 | N
2026-006 | ST008 | Payoff Indemnification | Y | MM | 2026-02-28 | Y | LV | 2026-03-08 | N
2026-006 | ST009 | Privacy notice | Y | MM | 2026-02-27 | Y | LV | 2026-03-08 | N
2026-006 | ST010 | 1099 | Y | MM | 2026-03-10 | Y | LV | 2026-03-15 | N
2026-006 | ST011 | Owners' Title Ins. Notice | Y | MM | 2026-02-20 | Y | LV | 2026-03-06 | N
2026-006 | ST012 | 50 ways to lose your property | Y | MM | 2026-03-05 | Y | LV | 2026-02-24 | N
2026-006 | ST013 | Letter of Rep./Privity Disclaimer | Y | MM | 2026-02-27 | Y | LV | 2026-03-04 | N
2026-006 | ST014 | CPC Notice/Offer (OH-24.1 - 2 pages) | Y | MM | 2026-02-15 | Y | LV | 2026-02-24 | N
2026-006 | ST015 | Notice to Consumer re: mtg loan | Y | MM | 2026-02-24 | Y | LV | 2026-02-21 | N
2026-006 | ST016 | Closing Notice to Borrower | Y | MM | 2026-02-28 | Y | LV | 2026-03-12 | N
2026-006 | ST017 | Disbursement Instructions | Y | MM | 2026-03-05 | Y | LV | 2026-03-06 | N
2026-006 | ST018 | Unsecured Debt Indemnification | Y | MM | 2026-03-07 | Y | LV | 2026-02-25 | N
2026-006 | ST019 | Not Me Affidavit | Y | MM | 2026-03-01 | Y | LV | 2026-03-01 | N
2026-006 | ST020 | Memorandum of Trust | Y | MM | 2026-03-01 | Y | LV | 2026-03-08 | N
2026-006 | ST021 | LLC Resolution | Y | MM | 2026-02-21 | Y | LV | 2026-03-03 | N
2026-006 | ST022 | Add'l Doc #1 | Y | MM | 2026-03-02 | Y | LV | 2026-03-12 | N
2026-006 | ST023 | Add'l Doc #2 | Y | MM | 2026-03-12 | Y | LV | 2026-03-10 | N
2026-006 | FIN001 | Numbers balance with Lender | Y | MM | 2026-02-20 | Y | LV | 2026-03-08 | N
2026-006 | FIN002 | Changed Docs to Kemba/EFCU | Y | MM | 2026-02-17 | Y | LV | 2026-02-24 | N
2026-006 | FIN003 | SS sent to agents | Y | MM | 2026-03-03 | Y | LV | 2026-03-08 | N
2026-006 | FIN004 | Copies | Y | MM | 2026-03-07 | Y | LV | 2026-03-06 | N
2026-006 | FIN005 | Checks | Y | MM | 2026-02-25 | Y | LV | 2026-02-17 | N
2026-006 | POST001 | HUD | Y | MM | 2026-03-11 | Y | LV | 2026-02-22 | N
2026-006 | POST002 | Deed | Y | MM | 2026-03-08 | Y | LV | 2026-02-24 | N
2026-006 | POST003 | Mortgage | Y | MM | 2026-02-22 | Y | LV | 2026-03-12 | N
2026-006 | POST004 | Note | Y | MM | 2026-02-21 | Y | LV | 2026-02-19 | N
2026-006 | POST005 | Subordination | Y | MM | 2026-02-15 | Y | LV | 2026-02-16 | N
2026-006 | POST006 | Notice of RTC | Y | MM | 2026-02-22 | Y | LV | 2026-03-02 | N
2026-006 | POST007 | Tax ID on 1099/Closing Affidavit | Y | MM | 2026-03-06 | Y | LV | 2026-03-14 | N
2026-006 | POST008 | Copies of drivers licenses | Y | MM | 2026-03-11 | Y | LV | 2026-02-17 | N
2026-006 | POST009 | Funds: Buyer / Lender / Seller | Y | MM | 2026-03-01 | Y | LV | 2026-02-28 | N
2026-006 | POST010 | Satisfaction | Y | MM | 2026-03-07 | Y | LV | 2026-03-05 | N
2026-006 | POST011 | Memorandum of Trust | Y | MM | 2026-02-21 | Y | LV | 2026-03-09 | N
2026-006 | POST012 | Power of Attorney | Y | MM | 2026-03-09 | Y | LV | 2026-02-27 | N
2026-006 | POST013 | Other | Y | MM | 2026-03-02 | Y | LV | 2026-02-27 | N

## PhaseTaskStatus
Phase Task Status — per matter
Prepared = task done; Approved = reviewed/finalized; NA = task does not apply.
MatterID | TaskKey | TaskName | Prepared | PreparedInitials | PreparedDate | Approved | ApprovedInitials | ApprovedDate | NA | Notes
2026-001 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | Y | MM | 2026-04-17 | Y | LV | 2026-04-19 | N
2026-001 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | Y | MM | 2026-04-20 | Y | LV | 2026-04-20 | N
2026-001 | P1.03 | Confirm earnest money deposited | Y | MM | 2026-04-25 | N |  |  | N
2026-001 | P1.04 | Review title exam | Y | MM | 2026-04-25 | Y | LV | 2026-04-21 | N
2026-001 | P1.06 | Prepare commitment | Y | MM | 2026-04-18 | N |  |  | N
2026-001 | P1.07 | Issue CPC letter to lender | Y | MM | 2026-04-24 | Y | LV | 2026-04-26 | N
2026-001 | P1.08b | Issue CPC letter to buyer (on request) | Y | MM | 2026-04-22 | N |  |  | N
2026-001 | P1.09b | Issue CPC letter to seller (on request) | Y | MM | 2026-04-24 | N |  |  | N
2026-001 | P1.10 | Send title commitment / opinion letter to client | Y | MM | 2026-04-25 | Y | LV | 2026-04-24 | N
2026-001 | P1.11 | Gather tax / HOA / utility prorations | Y | MM | 2026-04-25 | N |  |  | N
2026-001 | P1.12 | Prepare preliminary CD | Y | MM | 2026-04-19 | Y | LV | 2026-04-25 | N
2026-001 | P1.14 | Email to lender — docs + SAI wire info | Y | MM | 2026-04-20 | Y | LV | 2026-04-22 | N
2026-001 | P2.01 | Order survey | N |  |  | N |  |  | N
2026-001 | P2.02 | Receive and review survey | N |  |  | N |  |  | N
2026-001 | P2.03 | Request payoff letter | N |  |  | N |  |  | N
2026-001 | P2.04 | Receive and verify payoff letter | N |  |  | N |  |  | N
2026-001 | P2.05 | Prepare deed | N |  |  | N |  |  | N
2026-001 | P2.06 | Prepare mortgage / note | N |  |  | N |  |  | N
2026-001 | P2.07 | Prepare state-specific disclosure forms | N |  |  | N |  |  | N
2026-001 | P2.08 | Request HOA / condo association documents | N |  |  | N |  |  | N
2026-001 | P2.09 | Confirm closing logistics — local parties, local closing? | N |  |  | N |  |  | N
2026-001 | P2.10 | Schedule remote online notary OR call BankServ for notary | N |  |  | N |  |  | N
2026-001 | P2.11 | Obtain initial fees from lender | N |  |  | N |  |  | N
2026-001 | P2.12 | Confirm documents to prepare for lender | N |  |  | N |  |  | N
2026-001 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | N |  |  | N |  |  | N
2026-001 | P3.02 | Balance funding with lender; obtain final approval to close | N |  |  | N |  |  | N
2026-001 | P3.03 | Obtain lender-prepared documents | N |  |  | N |  |  | N
2026-001 | P3.04 | Tab / prep notary blocks on documents | N |  |  | N |  |  | N
2026-001 | P3.05 | Approve and print all closing documents | N |  |  | N |  |  | N
2026-001 | P3.06 | Conduct closing / obtain signatures | N |  |  | N |  |  | N
2026-001 | P3.07 | Confirm receipt of all funds | N |  |  | N |  |  | N
2026-001 | P3.08 | Add receipts and disbursements to ledger | N |  |  | N |  |  | N
2026-001 | P3.09 | Prepare outgoing wire checklist | N |  |  | N |  |  | N
2026-001 | P3.10 | Cut checks | N |  |  | N |  |  | N
2026-001 | P3.11 | Complete disbursements | N |  |  | N |  |  | N
2026-001 | P3.12 | Copy checks to net docs (or delegate to paralegal) | N |  |  | N |  |  | N
2026-001 | P3.13 | Tax ID form (1099) | N |  |  | N |  |  | N
2026-002 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | Y | MM | 2026-05-11 | Y | LV | 2026-05-11 | N
2026-002 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | Y | MM | 2026-05-07 | Y | LV | 2026-05-11 | N
2026-002 | P1.03 | Confirm earnest money deposited | Y | MM | 2026-05-07 | Y | LV | 2026-05-07 | N
2026-002 | P1.04 | Review title exam | Y | MM | 2026-05-08 | Y | LV | 2026-05-12 | N
2026-002 | P1.05 | Prepare opinion letter | Y | MM | 2026-05-05 | Y | LV | 2026-05-07 | N
2026-002 | P1.10 | Send title commitment / opinion letter to client | Y | MM | 2026-05-05 | Y | LV | 2026-05-07 | N
2026-002 | P1.11 | Gather tax / HOA / utility prorations | Y | MM | 2026-05-09 | Y | LV | 2026-05-09 | N
2026-002 | P1.12 | Prepare preliminary CD | Y | MM | 2026-05-09 | Y | LV | 2026-05-04 | N
2026-002 | P1.13 | Prepare tax information sheet | Y | MM | 2026-05-09 | Y | LV | 2026-05-10 | N
2026-002 | P1.14b | Email to lender — docs + RKPT wire info | Y | MM | 2026-05-03 | N |  |  | N
2026-002 | P2.01 | Order survey | N |  |  | N |  |  | N
2026-002 | P2.02 | Receive and review survey | N |  |  | N |  |  | N
2026-002 | P2.03 | Request payoff letter | N |  |  | N |  |  | N
2026-002 | P2.04 | Receive and verify payoff letter | Y | MM | 2026-05-08 | N |  |  | N
2026-002 | P2.05 | Prepare deed | Y | MM | 2026-05-09 | N |  |  | N
2026-002 | P2.06 | Prepare mortgage / note | N |  |  | N |  |  | N
2026-002 | P2.07 | Prepare state-specific disclosure forms | N |  |  | N |  |  | N
2026-002 | P2.08 | Request HOA / condo association documents | N |  |  | N |  |  | N
2026-002 | P2.09 | Confirm closing logistics — local parties, local closing? | N |  |  | N |  |  | N
2026-002 | P2.10 | Schedule remote online notary OR call BankServ for notary | N |  |  | N |  |  | N
2026-002 | P2.11 | Obtain initial fees from lender | N |  |  | N |  |  | N
2026-002 | P2.12 | Confirm documents to prepare for lender | Y | MM | 2026-05-06 | N |  |  | N
2026-002 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | N |  |  | N |  |  | N
2026-002 | P3.02 | Balance funding with lender; obtain final approval to close | N |  |  | N |  |  | N
2026-002 | P3.03 | Obtain lender-prepared documents | N |  |  | N |  |  | N
2026-002 | P3.04 | Tab / prep notary blocks on documents | N |  |  | N |  |  | N
2026-002 | P3.05 | Approve and print all closing documents | N |  |  | N |  |  | N
2026-002 | P3.06 | Conduct closing / obtain signatures | N |  |  | N |  |  | N
2026-002 | P3.07 | Confirm receipt of all funds | N |  |  | N |  |  | N
2026-002 | P3.08 | Add receipts and disbursements to ledger | N |  |  | N |  |  | N
2026-002 | P3.09 | Prepare outgoing wire checklist | N |  |  | N |  |  | N
2026-002 | P3.10 | Cut checks | N |  |  | N |  |  | N
2026-002 | P3.11 | Complete disbursements | N |  |  | N |  |  | N
2026-002 | P3.12 | Copy checks to net docs (or delegate to paralegal) | N |  |  | N |  |  | N
2026-002 | P3.13 | Tax ID form (1099) | N |  |  | N |  |  | N
2026-003 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | N |  |  | N |  |  | N
2026-003 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | N |  |  | N |  |  | N
2026-003 | P1.03 | Confirm earnest money deposited | N |  |  | N |  |  | N
2026-003 | P1.04 | Review title exam | N |  |  | N |  |  | N
2026-003 | P1.06 | Prepare commitment | N |  |  | N |  |  | N
2026-003 | P1.07 | Issue CPC letter to lender | N |  |  | N |  |  | N
2026-003 | P1.08 | Issue CPC letter to buyer | N |  |  | N |  |  | N
2026-003 | P1.08b | Issue CPC letter to buyer (on request) | N |  |  | N |  |  | N
2026-003 | P1.09 | Issue CPC letter to seller | N |  |  | N |  |  | N
2026-003 | P1.09b | Issue CPC letter to seller (on request) | N |  |  | N |  |  | N
2026-003 | P1.10 | Send title commitment / opinion letter to client | N |  |  | N |  |  | N
2026-003 | P1.11 | Gather tax / HOA / utility prorations | N |  |  | N |  |  | N
2026-003 | P1.12c | Prepare preliminary settlement statement | N |  |  | N |  |  | N
2026-003 | P1.14 | Email to lender — docs + SAI wire info | N |  |  | N |  |  | N
2026-003 | P2.01 | Order survey | N |  |  | N |  |  | N
2026-003 | P2.02 | Receive and review survey | N |  |  | N |  |  | N
2026-003 | P2.03 | Request payoff letter | N |  |  | N |  |  | N
2026-003 | P2.04 | Receive and verify payoff letter | N |  |  | N |  |  | N
2026-003 | P2.05 | Prepare deed | N |  |  | N |  |  | N
2026-003 | P2.06 | Prepare mortgage / note | N |  |  | N |  |  | N
2026-003 | P2.07 | Prepare state-specific disclosure forms | N |  |  | N |  |  | N
2026-003 | P2.08 | Request HOA / condo association documents | N |  |  | N |  |  | N
2026-003 | P2.09 | Confirm closing logistics — local parties, local closing? | N |  |  | N |  |  | N
2026-003 | P2.10 | Schedule remote online notary OR call BankServ for notary | N |  |  | N |  |  | N
2026-003 | P2.11 | Obtain initial fees from lender | N |  |  | N |  |  | N
2026-003 | P2.12 | Confirm documents to prepare for lender | N |  |  | N |  |  | N
2026-003 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | N |  |  | N |  |  | N
2026-003 | P3.02 | Balance funding with lender; obtain final approval to close | N |  |  | N |  |  | N
2026-003 | P3.03 | Obtain lender-prepared documents | N |  |  | N |  |  | N
2026-003 | P3.04 | Tab / prep notary blocks on documents | N |  |  | N |  |  | N
2026-003 | P3.05 | Approve and print all closing documents | N |  |  | N |  |  | N
2026-003 | P3.06 | Conduct closing / obtain signatures | N |  |  | N |  |  | N
2026-003 | P3.07 | Confirm receipt of all funds | N |  |  | N |  |  | N
2026-003 | P3.08 | Add receipts and disbursements to ledger | N |  |  | N |  |  | N
2026-003 | P3.09 | Prepare outgoing wire checklist | N |  |  | N |  |  | N
2026-003 | P3.10 | Cut checks | N |  |  | N |  |  | N
2026-003 | P3.11 | Complete disbursements | N |  |  | N |  |  | N
2026-003 | P3.12 | Copy checks to net docs (or delegate to paralegal) | N |  |  | N |  |  | N
2026-003 | P3.13 | Tax ID form (1099) | N |  |  | N |  |  | N
2026-004 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | N |  |  | N |  |  | N
2026-004 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | N |  |  | N |  |  | N
2026-004 | P1.03 | Confirm earnest money deposited | N |  |  | N |  |  | N
2026-004 | P1.04 | Review title exam | N |  |  | N |  |  | N
2026-004 | P1.06 | Prepare commitment | N |  |  | N |  |  | N
2026-004 | P1.08b | Issue CPC letter to buyer (on request) | N |  |  | N |  |  | N
2026-004 | P1.09b | Issue CPC letter to seller (on request) | N |  |  | N |  |  | N
2026-004 | P1.10 | Send title commitment / opinion letter to client | N |  |  | N |  |  | N
2026-004 | P1.11 | Gather tax / HOA / utility prorations | N |  |  | N |  |  | N
2026-004 | P1.12d | Prepare preliminary settlement statement (cash sale) | N |  |  | N |  |  | N
2026-004 | P2.01 | Order survey | N |  |  | N |  |  | N
2026-004 | P2.02 | Receive and review survey | N |  |  | N |  |  | N
2026-004 | P2.03 | Request payoff letter | N |  |  | N |  |  | N
2026-004 | P2.04 | Receive and verify payoff letter | N |  |  | N |  |  | N
2026-004 | P2.05 | Prepare deed | N |  |  | N |  |  | N
2026-004 | P2.07 | Prepare state-specific disclosure forms | N |  |  | N |  |  | N
2026-004 | P2.08 | Request HOA / condo association documents | N |  |  | N |  |  | N
2026-004 | P2.09 | Confirm closing logistics — local parties, local closing? | N |  |  | N |  |  | N
2026-004 | P2.10 | Schedule remote online notary OR call BankServ for notary | N |  |  | N |  |  | N
2026-004 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | N |  |  | N |  |  | N
2026-004 | P3.04 | Tab / prep notary blocks on documents | N |  |  | N |  |  | N
2026-004 | P3.05 | Approve and print all closing documents | N |  |  | N |  |  | N
2026-004 | P3.06 | Conduct closing / obtain signatures | N |  |  | N |  |  | N
2026-004 | P3.07 | Confirm receipt of all funds | N |  |  | N |  |  | N
2026-004 | P3.08 | Add receipts and disbursements to ledger | N |  |  | N |  |  | N
2026-004 | P3.09 | Prepare outgoing wire checklist | N |  |  | N |  |  | N
2026-004 | P3.10 | Cut checks | N |  |  | N |  |  | N
2026-004 | P3.11 | Complete disbursements | N |  |  | N |  |  | N
2026-004 | P3.12 | Copy checks to net docs (or delegate to paralegal) | N |  |  | N |  |  | N
2026-004 | P3.13 | Tax ID form (1099) | N |  |  | N |  |  | N
2026-005 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | N |  |  | N |  |  | N
2026-005 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | N |  |  | N |  |  | N
2026-005 | P1.03 | Confirm earnest money deposited | N |  |  | N |  |  | N
2026-005 | P1.04 | Review title exam | N |  |  | N |  |  | N
2026-005 | P1.05 | Prepare opinion letter | N |  |  | N |  |  | N
2026-005 | P1.10 | Send title commitment / opinion letter to client | N |  |  | N |  |  | N
2026-005 | P1.11 | Gather tax / HOA / utility prorations | N |  |  | N |  |  | N
2026-005 | P1.12 | Prepare preliminary CD | N |  |  | N |  |  | N
2026-005 | P1.14b | Email to lender — docs + RKPT wire info | N |  |  | N |  |  | N
2026-005 | P2.01 | Order survey | N |  |  | N |  |  | N
2026-005 | P2.02 | Receive and review survey | N |  |  | N |  |  | N
2026-005 | P2.03 | Request payoff letter | N |  |  | N |  |  | N
2026-005 | P2.04 | Receive and verify payoff letter | N |  |  | N |  |  | N
2026-005 | P2.05 | Prepare deed | N |  |  | N |  |  | N
2026-005 | P2.06 | Prepare mortgage / note | N |  |  | N |  |  | N
2026-005 | P2.07 | Prepare state-specific disclosure forms | N |  |  | N |  |  | N
2026-005 | P2.08 | Request HOA / condo association documents | N |  |  | N |  |  | N
2026-005 | P2.09 | Confirm closing logistics — local parties, local closing? | N |  |  | N |  |  | N
2026-005 | P2.10 | Schedule remote online notary OR call BankServ for notary | N |  |  | N |  |  | N
2026-005 | P2.11 | Obtain initial fees from lender | N |  |  | N |  |  | N
2026-005 | P2.12 | Confirm documents to prepare for lender | N |  |  | N |  |  | N
2026-005 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | N |  |  | N |  |  | N
2026-005 | P3.02 | Balance funding with lender; obtain final approval to close | N |  |  | N |  |  | N
2026-005 | P3.03 | Obtain lender-prepared documents | N |  |  | N |  |  | N
2026-005 | P3.04 | Tab / prep notary blocks on documents | N |  |  | N |  |  | N
2026-005 | P3.05 | Approve and print all closing documents | N |  |  | N |  |  | N
2026-005 | P3.06 | Conduct closing / obtain signatures | N |  |  | N |  |  | N
2026-005 | P3.07 | Confirm receipt of all funds | N |  |  | N |  |  | N
2026-005 | P3.08 | Add receipts and disbursements to ledger | N |  |  | N |  |  | N
2026-005 | P3.09 | Prepare outgoing wire checklist | N |  |  | N |  |  | N
2026-005 | P3.10 | Cut checks | N |  |  | N |  |  | N
2026-005 | P3.11 | Complete disbursements | N |  |  | N |  |  | N
2026-005 | P3.12 | Copy checks to net docs (or delegate to paralegal) | N |  |  | N |  |  | N
2026-005 | P3.13 | Tax ID form (1099) | N |  |  | N |  |  | N
2026-006 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | Y | MM | 2026-02-16 | Y | LV | 2026-02-19 | N
2026-006 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | Y | MM | 2026-02-19 | Y | LV | 2026-02-13 | N
2026-006 | P1.03 | Confirm earnest money deposited | Y | MM | 2026-02-18 | Y | LV | 2026-02-18 | N
2026-006 | P1.04 | Review title exam | Y | MM | 2026-02-18 | Y | LV | 2026-02-15 | N
2026-006 | P1.06 | Prepare commitment | Y | MM | 2026-02-19 | Y | LV | 2026-02-15 | N
2026-006 | P1.07 | Issue CPC letter to lender | Y | MM | 2026-02-20 | Y | LV | 2026-02-13 | N
2026-006 | P1.08b | Issue CPC letter to buyer (on request) | Y | MM | 2026-02-18 | Y | LV | 2026-02-22 | N
2026-006 | P1.09b | Issue CPC letter to seller (on request) | Y | MM | 2026-02-12 | Y | LV | 2026-02-14 | N
2026-006 | P1.10 | Send title commitment / opinion letter to client | Y | MM | 2026-02-18 | Y | LV | 2026-02-15 | N
2026-006 | P1.11 | Gather tax / HOA / utility prorations | Y | MM | 2026-02-19 | Y | LV | 2026-02-15 | N
2026-006 | P1.12 | Prepare preliminary CD | Y | MM | 2026-02-12 | Y | LV | 2026-02-17 | N
2026-006 | P1.14 | Email to lender — docs + SAI wire info | Y | MM | 2026-02-18 | Y | LV | 2026-02-18 | N
2026-006 | P2.01 | Order survey | Y | MM | 2026-02-15 | Y | LV | 2026-02-20 | N
2026-006 | P2.02 | Receive and review survey | Y | MM | 2026-02-17 | Y | LV | 2026-02-18 | N
2026-006 | P2.03 | Request payoff letter | Y | MM | 2026-02-18 | Y | LV | 2026-02-17 | N
2026-006 | P2.04 | Receive and verify payoff letter | Y | MM | 2026-02-18 | Y | LV | 2026-02-17 | N
2026-006 | P2.05 | Prepare deed | Y | MM | 2026-02-13 | Y | LV | 2026-02-20 | N
2026-006 | P2.06 | Prepare mortgage / note | Y | MM | 2026-02-12 | Y | LV | 2026-02-21 | N
2026-006 | P2.07 | Prepare state-specific disclosure forms | Y | MM | 2026-02-12 | Y | LV | 2026-02-18 | N
2026-006 | P2.08 | Request HOA / condo association documents | Y | MM | 2026-02-15 | Y | LV | 2026-02-14 | N
2026-006 | P2.09 | Confirm closing logistics — local parties, local closing? | Y | MM | 2026-02-12 | Y | LV | 2026-02-13 | N
2026-006 | P2.10 | Schedule remote online notary OR call BankServ for notary | Y | MM | 2026-02-15 | Y | LV | 2026-02-16 | N
2026-006 | P2.11 | Obtain initial fees from lender | Y | MM | 2026-02-12 | Y | LV | 2026-02-22 | N
2026-006 | P2.12 | Confirm documents to prepare for lender | Y | MM | 2026-02-14 | Y | LV | 2026-02-16 | N
2026-006 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | Y | MM | 2026-02-14 | Y | LV | 2026-02-20 | N
2026-006 | P3.02 | Balance funding with lender; obtain final approval to close | Y | MM | 2026-02-13 | Y | LV | 2026-02-22 | N
2026-006 | P3.03 | Obtain lender-prepared documents | Y | MM | 2026-02-15 | Y | LV | 2026-02-20 | N
2026-006 | P3.04 | Tab / prep notary blocks on documents | Y | MM | 2026-02-16 | Y | LV | 2026-02-18 | N
2026-006 | P3.05 | Approve and print all closing documents | Y | MM | 2026-02-14 | Y | LV | 2026-02-22 | N
2026-006 | P3.06 | Conduct closing / obtain signatures | Y | MM | 2026-02-13 | Y | LV | 2026-02-15 | N
2026-006 | P3.07 | Confirm receipt of all funds | Y | MM | 2026-02-16 | Y | LV | 2026-02-14 | N
2026-006 | P3.08 | Add receipts and disbursements to ledger | Y | MM | 2026-02-12 | Y | LV | 2026-02-17 | N
2026-006 | P3.09 | Prepare outgoing wire checklist | Y | MM | 2026-02-18 | Y | LV | 2026-02-19 | N
2026-006 | P3.10 | Cut checks | Y | MM | 2026-02-15 | Y | LV | 2026-02-14 | N
2026-006 | P3.11 | Complete disbursements | Y | MM | 2026-02-15 | Y | LV | 2026-02-14 | N
2026-006 | P3.12 | Copy checks to net docs (or delegate to paralegal) | Y | MM | 2026-02-16 | Y | LV | 2026-02-22 | N
2026-006 | P3.13 | Tax ID form (1099) | Y | MM | 2026-02-13 | Y | LV | 2026-02-22 | N

## Phases
Phase Definitions
Lillian's three-phase workflow model. Edit via app Settings.
PhaseNumber | PhaseName | PhaseShortName | PhaseDescription
1 | Intake & Disclosure | Intake | Connecting with interested parties, performing logistics, providing preliminary numbers.
2 | Document Prep | Prep | Document preparation and information gathering.
3 | Closing & Disbursement | Closing | The act of closing: cutting checks, confirming funds, backup wire documents, disbursements.

## PhaseTasks
Phase Tasks — task template per phase
Conditions: FileType (RK/ST/Either), DealType (Res./Comm./Cash/Any), LenderRequirement (HasLender/NoLender/Specific/Any), SpecificLenderName, State (KY/OH/IN/Any), IsOptional (Y = appears as "on request" subsection, not required for phase completion).
PhaseNumber | TaskOrder | TaskKey | TaskName | FileType | DealType | LenderRequirement | SpecificLenderName | State | IsOptional | Notes
1 | 10 | P1.01 | Confirm receipt of executed purchase agreement / loan documents | Either | Any | Any |  | Any | N
1 | 20 | P1.02 | Identify all parties (buyer, seller, lender, brokers, opposing counsel) | Either | Any | Any |  | Any | N
1 | 30 | P1.03 | Confirm earnest money deposited | Either | Any | Any |  | Any | N | Mark N/A on the matter if no earnest money.
1 | 40 | P1.04 | Review title exam | Either | Any | Any |  | Any | N
1 | 50 | P1.05 | Prepare opinion letter | RK | Any | Any |  | Any | N | RK files only.
1 | 60 | P1.06 | Prepare commitment | ST | Any | Any |  | Any | N | ST files only.
1 | 70 | P1.07 | Issue CPC letter to lender | ST | Any | HasLender |  | Any | N | ST with a lender.
1 | 80 | P1.08 | Issue CPC letter to buyer | ST | Any | Any |  | IN | N | Required for Indiana ST files.
1 | 81 | P1.08b | Issue CPC letter to buyer (on request) | ST | Any | Any |  | Any | Y | Non-Indiana ST files — buyer may request.
1 | 90 | P1.09 | Issue CPC letter to seller | ST | Any | Any |  | IN | N | Required for Indiana ST files.
1 | 91 | P1.09b | Issue CPC letter to seller (on request) | ST | Any | Any |  | Any | Y | Non-Indiana ST files — seller may request.
1 | 100 | P1.10 | Send title commitment / opinion letter to client | Either | Any | Any |  | Any | N
1 | 110 | P1.11 | Gather tax / HOA / utility prorations | Either | Any | Any |  | Any | N
1 | 120 | P1.12 | Prepare preliminary CD | Either | Res. | HasLender |  | Any | N | Residential with a lender.
1 | 121 | P1.12b | Prepare preliminary CD (Comm. Sharefax) | Either | Comm. | Specific | Sharefax | Any | N | Commercial only when lender = Sharefax.
1 | 122 | P1.12c | Prepare preliminary settlement statement | Either | Comm. | Any |  | Any | N | Used unless P1.12b applies.
1 | 123 | P1.12d | Prepare preliminary settlement statement (cash sale) | Either | Cash | NoLender |  | Any | N | Cash sales — no lender.
1 | 130 | P1.13 | Prepare tax information sheet | Either | Any | Specific | Sharefax | Any | N | Sharefax-specific document.
1 | 140 | P1.14 | Email to lender — docs + SAI wire info | ST | Any | HasLender |  | Any | N | SAI wire info for ST files.
1 | 141 | P1.14b | Email to lender — docs + RKPT wire info | RK | Any | HasLender |  | Any | N | RKPT wire info for RK files.
2 | 10 | P2.01 | Order survey | Either | Any | Any |  | Any | N | Mark N/A if no survey required.
2 | 20 | P2.02 | Receive and review survey | Either | Any | Any |  | Any | N
2 | 30 | P2.03 | Request payoff letter | Either | Any | Any |  | Any | N | Mark N/A if no existing mortgage.
2 | 40 | P2.04 | Receive and verify payoff letter | Either | Any | Any |  | Any | N
2 | 50 | P2.05 | Prepare deed | Either | Any | Any |  | Any | N | Purchase matters; N/A for refinances.
2 | 60 | P2.06 | Prepare mortgage / note | Either | Any | HasLender |  | Any | N | Lender-specific format may apply — see Notes on matter.
2 | 70 | P2.07 | Prepare state-specific disclosure forms | Either | Any | Any |  | Any | N | KY: Protect My KY Home. IN: Sales Disclosure + Form 51781. OH: Conveyance Statement.
2 | 80 | P2.08 | Request HOA / condo association documents | Either | Any | Any |  | Any | N | Mark N/A if no HOA/condo.
2 | 90 | P2.09 | Confirm closing logistics — local parties, local closing? | Either | Any | Any |  | Any | N | Determines whether remote notary or BankServ is needed.
2 | 100 | P2.10 | Schedule remote online notary OR call BankServ for notary | Either | Any | Any |  | Any | N | Mark N/A if 2.09 confirmed local closing.
2 | 110 | P2.11 | Obtain initial fees from lender | Either | Any | HasLender |  | Any | N
2 | 120 | P2.12 | Confirm documents to prepare for lender | Either | Any | HasLender |  | Any | N
3 | 10 | P3.01 | Email all parties: date, time, location, what to bring, wire instructions | Either | Any | Any |  | Any | N
3 | 20 | P3.02 | Balance funding with lender; obtain final approval to close | Either | Any | HasLender |  | Any | N
3 | 30 | P3.03 | Obtain lender-prepared documents | Either | Any | HasLender |  | Any | N
3 | 40 | P3.04 | Tab / prep notary blocks on documents | Either | Any | Any |  | Any | N
3 | 50 | P3.05 | Approve and print all closing documents | Either | Any | Any |  | Any | N
3 | 60 | P3.06 | Conduct closing / obtain signatures | Either | Any | Any |  | Any | N
3 | 70 | P3.07 | Confirm receipt of all funds | Either | Any | Any |  | Any | N
3 | 80 | P3.08 | Add receipts and disbursements to ledger | Either | Any | Any |  | Any | N
3 | 90 | P3.09 | Prepare outgoing wire checklist | Either | Any | Any |  | Any | N | Mark N/A if no outgoing wires.
3 | 100 | P3.10 | Cut checks | Either | Any | Any |  | Any | N | Mark N/A if no check disbursements.
3 | 110 | P3.11 | Complete disbursements | Either | Any | Any |  | Any | N
3 | 120 | P3.12 | Copy checks to net docs (or delegate to paralegal) | Either | Any | Any |  | Any | N
3 | 130 | P3.13 | Tax ID form (1099) | Either | Any | Any |  | Any | N | Mark N/A if no reportable proceeds.

## Paralegals
Paralegals
Manage via app Settings → Paralegals.
Name | Initials | Active | Notes
Missy | MM | Y

## NoteAuthors
Note Authors
Anyone who can post a note in the system. Manage via app Settings → Note Authors.
Name | Initials | Role | Active | Notes
Lillian Vrolijk | LV | Attorney | Y | Workbook owner
Missy | MM | Paralegal | Y

## Lenders
Lenders
Lender database. IsSharefax flags Sharefax (drives several conditional tasks). Manage via app Settings → Lenders.
LenderName | IsSharefax | Active | Notes
Sharefax | Y | Y | Triggers preliminary CD on Comm. deals and the tax information sheet.

## StateRules
State Rules
DRAFT values — please verify.
State | StateAbbr | AttorneyRequired | FundingType | RecordingOfficeName | TransferTaxStructure | RecordingTimelineDays | StateDisclosures | Notes
Kentucky | KY | Y | Wet | County Clerk | State transfer tax + sometimes municipal tax | 30 | Protect My Kentucky Home form; Preparer signature & Group Number on docs; Deed reference on mortgage; KY Municipal Tax (if applicable) | DRAFT — please verify.
Ohio | OH | N | Wet | County Recorder | County conveyance fee (varies by county) | 30 | Conveyance Statement; CPC Notice/Offer (OH-24.1); Dayton Disclosure of Violation Form (Dayton properties only) | DRAFT — please verify.
Indiana | IN | N | Wet | County Recorder | $5 transfer fee + $10 disclosure fee + $5 TIEFF | 30 | Sales Disclosure Form; State Form 51781 (Yellow); SSN statement on all recorded documents | DRAFT — please verify.

## ChecklistTemplate
Document Checklist Template — 90 items
The app stamps these onto each new matter.
ItemOrder | ItemKey | SectionName | ParentItem | ChecklistItem | StateRestriction | TxTypeRestriction
10 | GEN001 | General Documents |  | Title Commitment / Opinion Letter
20 | GEN002 | General Documents |  | Title Update Needed/Requested
30 | GEN003 | General Documents |  | Title Update Received
40 | GEN004 | General Documents |  | Proof of insurance
50 | GEN005 | General Documents |  | Survey
60 | GEN006 | General Documents |  | Deed
70 | GEN007 | General Documents |  | Ohio - Conveyance Statement | OH
80 | GEN008 | General Documents |  | CPC Letter
90 | GEN009 | General Documents |  | Indiana Sales Disclosure Form | IN
100 | GEN010 | General Documents |  | Indiana State Form 51781 (Yellow) | IN
110 | GEN011 | General Documents |  | Dayton - Disclosure of Violation Form | Dayton
120 | GEN012 | General Documents |  | KY - Protect My Kentucky Home Form | KY
130 | GEN013 | General Documents |  | Note
140 | GEN014 | General Documents |  | Mortgage
150 | GEN015 | General Documents | Mortgage | Short-Form & Copy of Master Mortgage
160 | GEN016 | General Documents | Mortgage | Master Mortgage Reference
170 | GEN017 | General Documents | Mortgage | Master Mortgage Acknowledgment
180 | GEN018 | General Documents | Mortgage | Names & marital status correct
190 | GEN019 | General Documents | Mortgage | Correct Legal Description Attached
200 | GEN020 | General Documents | Mortgage | Riders needed
210 | CD001 | Closing Statement / CD Items |  | Buyer CD / Seller CD / SS
220 | CD002 | Closing Statement / CD Items |  | SS & CD(s) numbers match
230 | CD003 | Closing Statement / CD Items |  | Place of closing (HUD / SS)
240 | CD004 | Closing Statement / CD Items |  | Payoffs
250 | CD005 | Closing Statement / CD Items | Payoffs | All mortgages being paid off
260 | CD006 | Closing Statement / CD Items | Payoffs | Enough interest being collected
270 | CD007 | Closing Statement / CD Items |  | Earnest Money Credited Properly
280 | CD008 | Closing Statement / CD Items |  | Tax Proration
290 | CD009 | Closing Statement / CD Items |  | Property Taxes: Pay at closing?
300 | CD010 | Closing Statement / CD Items |  | Bank Charges Included
310 | CD011 | Closing Statement / CD Items |  | Title Insurance Premium
320 | CD012 | Closing Statement / CD Items |  | Refi / Reissue Rate |  | Refi
330 | CD013 | Closing Statement / CD Items |  | Endorsements
340 | CD014 | Closing Statement / CD Items |  | Recording Fees (E-Record?)
350 | CD015 | Closing Statement / CD Items |  | Transfer Fees
360 | CD016 | Closing Statement / CD Items |  | Document Preparation Fee
370 | CD017 | Closing Statement / CD Items |  | Commission
380 | CD018 | Closing Statement / CD Items |  | KY Municipal Tax | KY
390 | CD019 | Closing Statement / CD Items |  | IN - Transfer ($5), Disc ($10) & TIEFF ($5) | IN
400 | CD020 | Closing Statement / CD Items |  | Home Warranty
410 | CD021 | Closing Statement / CD Items |  | Seller Paid Closing Costs
420 | MISC001 | Miscellaneous |  | Title Issues - Resolved
430 | MISC002 | Miscellaneous |  | Refinance - 3 day rescission? |  | Refi
440 | MISC003 | Miscellaneous |  | Mortgage and Deed Names Match
450 | MISC004 | Miscellaneous |  | Correct legal attached
460 | MISC005 | Miscellaneous |  | KY - Preparer signature & Group Number | KY
470 | MISC006 | Miscellaneous |  | KY - Deed reference on mortgage | KY
480 | MISC007 | Miscellaneous |  | IN - SSN statement on all recorded docs | IN
490 | MISC008 | Miscellaneous |  | OFAC List / SDN / Patriot Search
500 | ST001 | Safe Title Documents |  | Agreement Regarding Prorations
510 | ST002 | Safe Title Documents |  | Compliance Agreement
520 | ST003 | Safe Title Documents |  | Survey Affidavit
530 | ST004 | Safe Title Documents |  | Survey Acknowledgment
540 | ST005 | Safe Title Documents |  | Closing Affidavit
550 | ST006 | Safe Title Documents |  | Tax Indemnification
560 | ST007 | Safe Title Documents |  | Payoff Letter / Statement(s)
570 | ST008 | Safe Title Documents |  | Payoff Indemnification
580 | ST009 | Safe Title Documents |  | Privacy notice
590 | ST010 | Safe Title Documents |  | 1099
600 | ST011 | Safe Title Documents |  | Owners' Title Ins. Notice
610 | ST012 | Safe Title Documents |  | 50 ways to lose your property
620 | ST013 | Safe Title Documents |  | Letter of Rep./Privity Disclaimer
630 | ST014 | Safe Title Documents |  | CPC Notice/Offer (OH-24.1 - 2 pages) | OH
640 | ST015 | Safe Title Documents |  | Notice to Consumer re: mtg loan
650 | ST016 | Safe Title Documents |  | Closing Notice to Borrower
660 | ST017 | Safe Title Documents |  | Disbursement Instructions
670 | ST018 | Safe Title Documents |  | Unsecured Debt Indemnification
680 | ST019 | Safe Title Documents |  | Not Me Affidavit
690 | ST020 | Safe Title Documents |  | Memorandum of Trust
700 | ST021 | Safe Title Documents |  | LLC Resolution
710 | ST022 | Safe Title Documents |  | Add'l Doc #1
720 | ST023 | Safe Title Documents |  | Add'l Doc #2
730 | FIN001 | Final Closing Items |  | Numbers balance with Lender
740 | FIN002 | Final Closing Items |  | Changed Docs to Kemba/EFCU
750 | FIN003 | Final Closing Items |  | SS sent to agents
760 | FIN004 | Final Closing Items |  | Copies
770 | FIN005 | Final Closing Items |  | Checks
780 | POST001 | Post Closing Checklist |  | HUD
790 | POST002 | Post Closing Checklist |  | Deed
800 | POST003 | Post Closing Checklist |  | Mortgage
810 | POST004 | Post Closing Checklist |  | Note
820 | POST005 | Post Closing Checklist |  | Subordination
830 | POST006 | Post Closing Checklist |  | Notice of RTC
840 | POST007 | Post Closing Checklist |  | Tax ID on 1099/Closing Affidavit
850 | POST008 | Post Closing Checklist |  | Copies of drivers licenses
860 | POST009 | Post Closing Checklist |  | Funds: Buyer / Lender / Seller
870 | POST010 | Post Closing Checklist |  | Satisfaction
880 | POST011 | Post Closing Checklist |  | Memorandum of Trust
890 | POST012 | Post Closing Checklist |  | Power of Attorney
900 | POST013 | Post Closing Checklist |  | Other

## FilterPresets
Filter Presets
Saved dashboard filter combinations. Managed via the app.
PresetID | PresetName | FilterJSON | CreatedDate
PR001 | Closing this week | {"quickChips":["closing_week"],"columnFilters":{},"statusFilter":"Active"} | 2026-05-29 00:43
PR002 | Sharefax deals | {"quickChips":["sharefax"],"columnFilters":{},"statusFilter":"Active"} | 2026-05-29 00:43

## Holidays
Federal Holidays — 2026
Used by the app for business-day calculations.
HolidayDate | HolidayName | IsObserved
2026-01-01 | New Year's Day | N
2026-01-19 | Martin Luther King Jr. Day | N
2026-02-16 | Presidents' Day | N
2026-05-25 | Memorial Day | N
2026-06-19 | Juneteenth | N
2026-07-03 | Independence Day (observed) | Y
2026-07-04 | Independence Day | N
2026-09-07 | Labor Day | N
2026-10-12 | Columbus Day | N
2026-11-11 | Veterans Day | N
2026-11-26 | Thanksgiving Day | N
2026-12-25 | Christmas Day | N

## TRIDCalendar
TRID Calendar — 2026
Reference data — the app computes dates dynamically.
CDDeliveryDate | EarliestSignDateHandDelivery | EarliestSignDateMailDelivery | Notes
2026-01-02 | 2026-01-06 | 2026-01-10
2026-01-03 | 2026-01-07 | 2026-01-10
2026-01-05 | 2026-01-08 | 2026-01-12
2026-01-06 | 2026-01-09 | 2026-01-13
2026-01-07 | 2026-01-10 | 2026-01-15
2026-01-08 | 2026-01-12 | 2026-01-16
2026-01-09 | 2026-01-13 | 2026-01-17
2026-01-10 | 2026-01-14 | 2026-01-17
2026-01-12 | 2026-01-15 | 2026-01-20
2026-01-13 | 2026-01-16 | 2026-01-21
2026-01-14 | 2026-01-17 | 2026-01-23
2026-01-15 | 2026-01-20 | 2026-01-24
2026-01-16 | 2026-01-21 | 2026-01-26
2026-01-17 | 2026-01-22 | 2026-01-26
2026-01-20 | 2026-01-23 | 2026-01-27
2026-01-21 | 2026-01-24 | 2026-01-29
2026-01-22 | 2026-01-26 | 2026-01-30
2026-01-23 | 2026-01-27 | 2026-01-31
2026-01-24 | 2026-01-28 | 2026-01-31
2026-01-26 | 2026-01-29 | 2026-02-02
2026-01-27 | 2026-01-30 | 2026-02-03
2026-01-28 | 2026-01-31 | 2026-02-05
2026-01-29 | 2026-02-02 | 2026-02-06
2026-01-30 | 2026-02-03 | 2026-02-07
2026-01-31 | 2026-02-04 | 2026-02-07
2026-02-02 | 2026-02-05 | 2026-02-09
2026-02-03 | 2026-02-06 | 2026-02-10
2026-02-04 | 2026-02-07 | 2026-02-12
2026-02-05 | 2026-02-09 | 2026-02-13
2026-02-06 | 2026-02-10 | 2026-02-14
2026-02-07 | 2026-02-11 | 2026-02-14
2026-02-09 | 2026-02-12 | 2026-02-17
2026-02-10 | 2026-02-13 | 2026-02-18
2026-02-11 | 2026-02-14 | 2026-02-20
2026-02-12 | 2026-02-17 | 2026-02-21
2026-02-13 | 2026-02-18 | 2026-02-23
2026-02-14 | 2026-02-19 | 2026-02-23
2026-02-17 | 2026-02-20 | 2026-02-24
2026-02-18 | 2026-02-21 | 2026-02-26
2026-02-19 | 2026-02-23 | 2026-02-27
2026-02-20 | 2026-02-24 | 2026-02-28
2026-02-21 | 2026-02-25 | 2026-02-28
2026-02-23 | 2026-02-26 | 2026-03-02
2026-02-24 | 2026-02-27 | 2026-03-03
2026-02-25 | 2026-02-28 | 2026-03-05
2026-02-26 | 2026-03-02 | 2026-03-06
2026-02-27 | 2026-03-03 | 2026-03-07
2026-02-28 | 2026-03-04 | 2026-03-07
2026-03-02 | 2026-03-05 | 2026-03-09
2026-03-03 | 2026-03-06 | 2026-03-10
2026-03-04 | 2026-03-07 | 2026-03-12
2026-03-05 | 2026-03-09 | 2026-03-13
2026-03-06 | 2026-03-10 | 2026-03-14
2026-03-07 | 2026-03-11 | 2026-03-14
2026-03-09 | 2026-03-12 | 2026-03-16
2026-03-10 | 2026-03-13 | 2026-03-17
2026-03-11 | 2026-03-14 | 2026-03-19
2026-03-12 | 2026-03-16 | 2026-03-20
2026-03-13 | 2026-03-17 | 2026-03-21
2026-03-14 | 2026-03-18 | 2026-03-21
2026-03-16 | 2026-03-19 | 2026-03-23
2026-03-17 | 2026-03-20 | 2026-03-24
2026-03-18 | 2026-03-21 | 2026-03-26
2026-03-19 | 2026-03-23 | 2026-03-27
2026-03-20 | 2026-03-24 | 2026-03-28
2026-03-21 | 2026-03-25 | 2026-03-28
2026-03-23 | 2026-03-26 | 2026-03-30
2026-03-24 | 2026-03-27 | 2026-03-31
2026-03-25 | 2026-03-28 | 2026-04-02
2026-03-26 | 2026-03-30 | 2026-04-03
2026-03-27 | 2026-03-31 | 2026-04-04
2026-03-28 | 2026-04-01 | 2026-04-04
2026-03-30 | 2026-04-02 | 2026-04-06
2026-03-31 | 2026-04-03 | 2026-04-07
2026-04-01 | 2026-04-04 | 2026-04-09
2026-04-02 | 2026-04-06 | 2026-04-10
2026-04-03 | 2026-04-07 | 2026-04-11
2026-04-04 | 2026-04-08 | 2026-04-11
2026-04-06 | 2026-04-09 | 2026-04-13
2026-04-07 | 2026-04-10 | 2026-04-14
2026-04-08 | 2026-04-11 | 2026-04-16
2026-04-09 | 2026-04-13 | 2026-04-17
2026-04-10 | 2026-04-14 | 2026-04-18
2026-04-11 | 2026-04-15 | 2026-04-18
2026-04-13 | 2026-04-16 | 2026-04-20
2026-04-14 | 2026-04-17 | 2026-04-21
2026-04-15 | 2026-04-18 | 2026-04-23
2026-04-16 | 2026-04-20 | 2026-04-24
2026-04-17 | 2026-04-21 | 2026-04-25
2026-04-18 | 2026-04-22 | 2026-04-25
2026-04-20 | 2026-04-23 | 2026-04-27
2026-04-21 | 2026-04-24 | 2026-04-28
2026-04-22 | 2026-04-25 | 2026-04-30
2026-04-23 | 2026-04-27 | 2026-05-01
2026-04-24 | 2026-04-28 | 2026-05-02
2026-04-25 | 2026-04-29 | 2026-05-02
2026-04-27 | 2026-04-30 | 2026-05-04
2026-04-28 | 2026-05-01 | 2026-05-05
2026-04-29 | 2026-05-02 | 2026-05-07
2026-04-30 | 2026-05-04 | 2026-05-08
2026-05-01 | 2026-05-05 | 2026-05-09
2026-05-02 | 2026-05-06 | 2026-05-09
2026-05-04 | 2026-05-07 | 2026-05-11
2026-05-05 | 2026-05-08 | 2026-05-12
2026-05-06 | 2026-05-09 | 2026-05-14
2026-05-07 | 2026-05-11 | 2026-05-15
2026-05-08 | 2026-05-12 | 2026-05-16
2026-05-09 | 2026-05-13 | 2026-05-16
2026-05-11 | 2026-05-14 | 2026-05-18
2026-05-12 | 2026-05-15 | 2026-05-19
2026-05-13 | 2026-05-16 | 2026-05-21
2026-05-14 | 2026-05-18 | 2026-05-22
2026-05-15 | 2026-05-19 | 2026-05-23
2026-05-16 | 2026-05-20 | 2026-05-23
2026-05-18 | 2026-05-21 | 2026-05-26
2026-05-19 | 2026-05-22 | 2026-05-27
2026-05-20 | 2026-05-23 | 2026-05-29
2026-05-21 | 2026-05-26 | 2026-05-30
2026-05-22 | 2026-05-27 | 2026-06-01
2026-05-23 | 2026-05-28 | 2026-06-01
2026-05-26 | 2026-05-29 | 2026-06-02
2026-05-27 | 2026-05-30 | 2026-06-04
2026-05-28 | 2026-06-01 | 2026-06-05
2026-05-29 | 2026-06-02 | 2026-06-06
2026-05-30 | 2026-06-03 | 2026-06-06
2026-06-01 | 2026-06-04 | 2026-06-08
2026-06-02 | 2026-06-05 | 2026-06-09
2026-06-03 | 2026-06-06 | 2026-06-11
2026-06-04 | 2026-06-08 | 2026-06-12
2026-06-05 | 2026-06-09 | 2026-06-13
2026-06-06 | 2026-06-10 | 2026-06-13
2026-06-08 | 2026-06-11 | 2026-06-15
2026-06-09 | 2026-06-12 | 2026-06-16
2026-06-10 | 2026-06-13 | 2026-06-18
2026-06-11 | 2026-06-15 | 2026-06-20
2026-06-12 | 2026-06-16 | 2026-06-22
2026-06-13 | 2026-06-17 | 2026-06-22
2026-06-15 | 2026-06-18 | 2026-06-23
2026-06-16 | 2026-06-20 | 2026-06-25
2026-06-17 | 2026-06-22 | 2026-06-26
2026-06-18 | 2026-06-23 | 2026-06-27
2026-06-20 | 2026-06-24 | 2026-06-27
2026-06-22 | 2026-06-25 | 2026-06-29
2026-06-23 | 2026-06-26 | 2026-06-30
2026-06-24 | 2026-06-27 | 2026-07-02
2026-06-25 | 2026-06-29 | 2026-07-06
2026-06-26 | 2026-06-30 | 2026-07-07
2026-06-27 | 2026-07-01 | 2026-07-07
2026-06-29 | 2026-07-02 | 2026-07-08
2026-06-30 | 2026-07-06 | 2026-07-09
2026-07-01 | 2026-07-07 | 2026-07-10
2026-07-02 | 2026-07-08 | 2026-07-11
2026-07-06 | 2026-07-09 | 2026-07-13
2026-07-07 | 2026-07-10 | 2026-07-14
2026-07-08 | 2026-07-11 | 2026-07-16
2026-07-09 | 2026-07-13 | 2026-07-17
2026-07-10 | 2026-07-14 | 2026-07-18
2026-07-11 | 2026-07-15 | 2026-07-18
2026-07-13 | 2026-07-16 | 2026-07-20
2026-07-14 | 2026-07-17 | 2026-07-21
2026-07-15 | 2026-07-18 | 2026-07-23
2026-07-16 | 2026-07-20 | 2026-07-24
2026-07-17 | 2026-07-21 | 2026-07-25
2026-07-18 | 2026-07-22 | 2026-07-25
2026-07-20 | 2026-07-23 | 2026-07-27
2026-07-21 | 2026-07-24 | 2026-07-28
2026-07-22 | 2026-07-25 | 2026-07-30
2026-07-23 | 2026-07-27 | 2026-07-31
2026-07-24 | 2026-07-28 | 2026-08-01
2026-07-25 | 2026-07-29 | 2026-08-01
2026-07-27 | 2026-07-30 | 2026-08-03
2026-07-28 | 2026-07-31 | 2026-08-04
2026-07-29 | 2026-08-01 | 2026-08-06
2026-07-30 | 2026-08-03 | 2026-08-07
2026-07-31 | 2026-08-04 | 2026-08-08
2026-08-01 | 2026-08-05 | 2026-08-08
2026-08-03 | 2026-08-06 | 2026-08-10
2026-08-04 | 2026-08-07 | 2026-08-11
2026-08-05 | 2026-08-08 | 2026-08-13
2026-08-06 | 2026-08-10 | 2026-08-14
2026-08-07 | 2026-08-11 | 2026-08-15
2026-08-08 | 2026-08-12 | 2026-08-15
2026-08-10 | 2026-08-13 | 2026-08-17
2026-08-11 | 2026-08-14 | 2026-08-18
2026-08-12 | 2026-08-15 | 2026-08-20
2026-08-13 | 2026-08-17 | 2026-08-21
2026-08-14 | 2026-08-18 | 2026-08-22
2026-08-15 | 2026-08-19 | 2026-08-22
2026-08-17 | 2026-08-20 | 2026-08-24
2026-08-18 | 2026-08-21 | 2026-08-25
2026-08-19 | 2026-08-22 | 2026-08-27
2026-08-20 | 2026-08-24 | 2026-08-28
2026-08-21 | 2026-08-25 | 2026-08-29
2026-08-22 | 2026-08-26 | 2026-08-29
2026-08-24 | 2026-08-27 | 2026-08-31
2026-08-25 | 2026-08-28 | 2026-09-01
2026-08-26 | 2026-08-29 | 2026-09-03
2026-08-27 | 2026-08-31 | 2026-09-04
2026-08-28 | 2026-09-01 | 2026-09-05
2026-08-29 | 2026-09-02 | 2026-09-05
2026-08-31 | 2026-09-03 | 2026-09-08
2026-09-01 | 2026-09-04 | 2026-09-09
2026-09-02 | 2026-09-05 | 2026-09-11
2026-09-03 | 2026-09-08 | 2026-09-12
2026-09-04 | 2026-09-09 | 2026-09-14
2026-09-05 | 2026-09-10 | 2026-09-14
2026-09-08 | 2026-09-11 | 2026-09-15
2026-09-09 | 2026-09-12 | 2026-09-17
2026-09-10 | 2026-09-14 | 2026-09-18
2026-09-11 | 2026-09-15 | 2026-09-19
2026-09-12 | 2026-09-16 | 2026-09-19
2026-09-14 | 2026-09-17 | 2026-09-21
2026-09-15 | 2026-09-18 | 2026-09-22
2026-09-16 | 2026-09-19 | 2026-09-24
2026-09-17 | 2026-09-21 | 2026-09-25
2026-09-18 | 2026-09-22 | 2026-09-26
2026-09-19 | 2026-09-23 | 2026-09-26
2026-09-21 | 2026-09-24 | 2026-09-28
2026-09-22 | 2026-09-25 | 2026-09-29
2026-09-23 | 2026-09-26 | 2026-10-01
2026-09-24 | 2026-09-28 | 2026-10-02
2026-09-25 | 2026-09-29 | 2026-10-03
2026-09-26 | 2026-09-30 | 2026-10-03
2026-09-28 | 2026-10-01 | 2026-10-05
2026-09-29 | 2026-10-02 | 2026-10-06
2026-09-30 | 2026-10-03 | 2026-10-08
2026-10-01 | 2026-10-05 | 2026-10-09
2026-10-02 | 2026-10-06 | 2026-10-10
2026-10-03 | 2026-10-07 | 2026-10-10
2026-10-05 | 2026-10-08 | 2026-10-13
2026-10-06 | 2026-10-09 | 2026-10-14
2026-10-07 | 2026-10-10 | 2026-10-16
2026-10-08 | 2026-10-13 | 2026-10-17
2026-10-09 | 2026-10-14 | 2026-10-19
2026-10-10 | 2026-10-15 | 2026-10-19
2026-10-13 | 2026-10-16 | 2026-10-20
2026-10-14 | 2026-10-17 | 2026-10-22
2026-10-15 | 2026-10-19 | 2026-10-23
2026-10-16 | 2026-10-20 | 2026-10-24
2026-10-17 | 2026-10-21 | 2026-10-24
2026-10-19 | 2026-10-22 | 2026-10-26
2026-10-20 | 2026-10-23 | 2026-10-27
2026-10-21 | 2026-10-24 | 2026-10-29
2026-10-22 | 2026-10-26 | 2026-10-30
2026-10-23 | 2026-10-27 | 2026-10-31
2026-10-24 | 2026-10-28 | 2026-10-31
2026-10-26 | 2026-10-29 | 2026-11-02
2026-10-27 | 2026-10-30 | 2026-11-03
2026-10-28 | 2026-10-31 | 2026-11-05
2026-10-29 | 2026-11-02 | 2026-11-06
2026-10-30 | 2026-11-03 | 2026-11-07
2026-10-31 | 2026-11-04 | 2026-11-07
2026-11-02 | 2026-11-05 | 2026-11-09
2026-11-03 | 2026-11-06 | 2026-11-10
2026-11-04 | 2026-11-07 | 2026-11-13
2026-11-05 | 2026-11-09 | 2026-11-14
2026-11-06 | 2026-11-10 | 2026-11-16
2026-11-07 | 2026-11-12 | 2026-11-16
2026-11-09 | 2026-11-13 | 2026-11-17
2026-11-10 | 2026-11-14 | 2026-11-19
2026-11-12 | 2026-11-16 | 2026-11-20
2026-11-13 | 2026-11-17 | 2026-11-21
2026-11-14 | 2026-11-18 | 2026-11-21
2026-11-16 | 2026-11-19 | 2026-11-23
2026-11-17 | 2026-11-20 | 2026-11-24
2026-11-18 | 2026-11-21 | 2026-11-27
2026-11-19 | 2026-11-23 | 2026-11-28
2026-11-20 | 2026-11-24 | 2026-11-30
2026-11-21 | 2026-11-25 | 2026-11-30
2026-11-23 | 2026-11-27 | 2026-12-01
2026-11-24 | 2026-11-28 | 2026-12-03
2026-11-25 | 2026-11-30 | 2026-12-04
2026-11-27 | 2026-12-01 | 2026-12-05
2026-11-28 | 2026-12-02 | 2026-12-05
2026-11-30 | 2026-12-03 | 2026-12-07
2026-12-01 | 2026-12-04 | 2026-12-08
2026-12-02 | 2026-12-05 | 2026-12-10
2026-12-03 | 2026-12-07 | 2026-12-11
2026-12-04 | 2026-12-08 | 2026-12-12
2026-12-05 | 2026-12-09 | 2026-12-12
2026-12-07 | 2026-12-10 | 2026-12-14
2026-12-08 | 2026-12-11 | 2026-12-15
2026-12-09 | 2026-12-12 | 2026-12-17
2026-12-10 | 2026-12-14 | 2026-12-18
2026-12-11 | 2026-12-15 | 2026-12-19
2026-12-12 | 2026-12-16 | 2026-12-19
2026-12-14 | 2026-12-17 | 2026-12-21
2026-12-15 | 2026-12-18 | 2026-12-22
2026-12-16 | 2026-12-19 | 2026-12-24
2026-12-17 | 2026-12-21 | 2026-12-26
2026-12-18 | 2026-12-22 | 2026-12-28
2026-12-19 | 2026-12-23 | 2026-12-28
2026-12-21 | 2026-12-24 | 2026-12-29
2026-12-22 | 2026-12-26 | 2026-12-31
2026-12-23 | 2026-12-28 | 2027-01-01
2026-12-24 | 2026-12-29 | 2027-01-02
2026-12-26 | 2026-12-30 | 2027-01-02
2026-12-28 | 2026-12-31 | 2027-01-04
2026-12-29 | 2027-01-01 | 2027-01-05
2026-12-30 | 2027-01-02 | 2027-01-07
2026-12-31 | 2027-01-04 | 2027-01-08

## _Meta
Metadata
Used by the web app.
SchemaVersion | 2.0
CurrentYear | 2026
DefaultState | Ohio
JeopardyDays | 5
LastModified | 2026-05-28 02:18:14
NextMatterSequence | 7
NextNoteSequence | 1
NextLenderSequence | 2
NextParalegalSequence | 2
NextAuthorSequence | 3
NextPhaseSequence | 4
NextTaskSequence | 1000
NextPresetSequence | 3